# Sales to onboarding handoff

Techmark Journal   Alvar Rodríguez   Reusable template and constructed example

Give delivery the commitments, people, and dependencies needed to identify the next action. Complete the handoff from the approved scope and ask the delivery owner to accept it before kickoff.

# Engagement

Client and engagement ID  [Enter here]

Approved scope reference and version  [Enter here]

Service and client outcome  [Enter here]

# Commitments

| Deliverable | Quantity and acceptance standard | Date and dependency |
| --- | --- | --- |
| [Deliverable] | [Quantity and agreed standard] | [Date or condition] |
| [Deliverable] | [Quantity and agreed standard] | [Date or condition] |
| [Deliverable] | [Quantity and agreed standard] | [Date or condition] |

Scope exclusions  [Record the agreed boundaries]

# People

| Role | Person and contact | Responsibility |
| --- | --- | --- |
| Client approver | [Name and contact] | [What this person may approve] |
| Delivery owner | [Name and contact] | Accept handoff and plan ready work |
| Account or sales owner | [Name and contact] | Confirm commitments and collect missing context |

# Inputs and readiness

Reusable template continued

Record what is still missing. Attach conditions to affected dates so a target is not mistaken for a commitment.

# Required inputs

| Input | Supplier or owner | Needed by | Acceptance check |
| --- | --- | --- | --- |
| [Input] | [Person] | [Date and timezone] | [Who checks what] |
| [Input] | [Person] | [Date and timezone] | [Who checks what] |
| [Input] | [Person] | [Date and timezone] | [Who checks what] |

# Open decisions

| Question or missing commitment | Decision owner | Needed by |
| --- | --- | --- |
| [Question and effect on the plan] | [Person] | [Date and timezone] |
| [Question and effect on the plan] | [Person] | [Date and timezone] |

# Next action

Action and responsible person  [Enter here]

Due date and timezone  [Enter here]

Affected dates if an input is late  [Enter here]

# Delivery acceptance

Confirm that delivery can identify the approved work, client approver, dependencies, and next action. Unresolved items stay visible with owners and dates.

Readiness  [Ready / Ready for preparation only / Needs clarification]

Accepted by and date  [Enter here]

Acceptance note  [Name any remaining condition or question]

# Completed handoff example

Constructed scenario   All names terms and dates are illustrative

The initial sales note was “Eight videos a month. Kickoff October 19. First batch October 26. Client will send assets.” The completed handoff adds the conditions delivery needs.

# Engagement

Client and engagement ID  Harbor Studio   DEMO-HO-01

Approved scope  DEMO-SCOPE-01 version 1   Illustrative approved scope reference

Service and client outcome  Recurring content production for the client’s social channels

# Commitments

| Deliverable | Quantity and acceptance standard | Date and dependency |
| --- | --- | --- |
| Monthly videos | Eight edited vertical videos, each 30–60 seconds | Monthly sequence agreed in DEMO-SCOPE-01 |
| First draft batch | Four drafts for client review | Target October 26, 2026 if required inputs arrive by October 20 |
| Revisions | One consolidated revision round per video | Client approver returns one consolidated response |

Scope exclusions  Filming and paid media management require separate scope.

Kickoff  October 19, 2026 at 10 a.m. Eastern Time. Planning may proceed; production still needs the inputs.

# People

| Role | Person | Responsibility |
| --- | --- | --- |
| Client approver | Casey Morgan | Approves scripts and final edits; supplies required assets |
| Delivery owner | Maya Chen | Accepts handoff and plans work against the approved scope |
| Account manager | Eli Brooks | Requests inputs, confirms receipt, and communicates date changes |

# Example inputs and acceptance

Completed handoff example continued

# Required inputs

| Input | Supplier | Needed by | Acceptance check |
| --- | --- | --- | --- |
| Source footage | Casey Morgan | October 20, 2026, noon ET | Eli checks files open and required footage is present |
| Brand guide | Casey Morgan | October 20, 2026, noon ET | Eli confirms current guide and usable brand assets |
| Asset permissions | Casey Morgan | October 20, 2026, noon ET | Eli confirms the agreed permission to use supplied assets is recorded |

# Open decisions

No unresolved commercial scope decision in this corrected example. Required assets are still pending. Any additional deliverable needs an approved scope change before a new commitment.

# Next action

Action  Eli sends Casey the complete input checklist before kickoff on October 19.

If inputs are late  Maya proposes a revised first-draft date after assessing the missing inputs; Eli communicates it before another promise is made.

# Delivery acceptance

Readiness  Ready for preparation only

Accepted by and date  Maya Chen   October 16, 2026   Constructed acceptance

The scope, approver, and next action are clear. Kickoff planning can proceed. Production and the October 26 target remain dependent on complete inputs by October 20.

# Source basis

Original operational template. Published context for connected handoffs and delivery responsibilities:

Attio   Sales led growth guide

GitLab   Professional Services Delivery Methodology