## ManufacturingOperationTask
Order Name | Item Name | Status Order | Quantity | Remaining Quantity | Units | Operation Sequence | Operation Name | Work Center Name | Machine Name | Schedule From Time | Due Time | Status Operation | Completed Quantity | Predecessor | Run Rate (Min/Unit) | Setup Time (Min)
#WO051 | RTY256LP | Released | 45 | 45 | Ea | 10 | Blending | Blending-Hub |  | 2024-09-20 13:09 | 2025-01-24 13:09 | Not Started | 0 |  | 0.6 | 30
#WO051 | RTY256LP | Released | 45 | 45 | Ea | 20 | Packaging | Packaging Hall |  | 2024-09-22 14:27 | 2025-01-24 13:09 | Not Started | 0 | Blending | 0.6 | 30
#WO082 | IKO185E | Released | 1 | 1 | Ea | 10 | Assembly | Assembly-Hub | A-Corner1 | 2024-10-07 15:15 | 2024-11-17 15:15 | Not Started | 0 |  | 4 | 15
#WO082 | IKO185E | Released | 1 | 1 | Ea | 20 | Packaging | Packaging Hall |  | 2024-10-08 15:10 | 2024-11-17 15:15 | Not Started | 0 | Assembly | 15 | 5
#WO102 | RTY256LP | Released | 28 | 28 | Ea | 10 | Blending | Blending-Hub |  | 2024-11-06 09:57 | 2024-12-08 09:57 | Not Started | 0 |  | 0.6 | 30
#WO102 | RTY256LP | Released | 28 | 28 | Ea | 20 | Packaging | Packaging Hall |  | 2024-11-08 08:51 | 2024-12-08 09:57 | Not Started | 0 | Blending | 0.6 | 15
#WO131 | RTY256LP | Released | 57 | 57 | Ea | 10 | Blending | Blending-Hub |  | 2024-10-01 11:13 | 2024-10-15 11:13 | Not Started | 0 |  | 0.6 | 30
#WO131 | RTY256LP | Released | 57 | 57 | Ea | 20 | Packaging | Packaging Hall | Hall-B | 2024-10-02 09:29 | 2024-10-15 11:13 | Not Started | 0 | Blending | 0.6 | 30
#WO151 | RTY256LP | Released | 20 | 20 | Ea | 10 | Blending | Blending-Hub |  | 2024-10-02 14:45 | 2024-10-15 11:13 | Not Started | 0 |  | 0.6 | 30
#WO151 | RTY256LP | Released | 20 | 20 | Ea | 20 | Packaging | Packaging Hall |  | 2024-10-04 11:15 | 2024-10-15 11:13 | Not Started | 0 | Blending | 0.6 | 30
#WO287 | IKO185E | Released | 2 | 2 | Ea | 10 | Assembly | Assembly-Hub |  | 2024-10-06 15:15 | 2024-11-27 15:15 | Not Started | 0 |  | 4 | 15
#WO382 | IKO185E | Released | 7 | 7 | Ea | 10 | Assembly | Assembly-Hub |  | 2024-10-16 16:35 | 2024-12-30 16:35 | Not Started | 0 |  | 4 | 15
#WO382 | IKO185E | Released | 7 | 7 | Ea | 20 | Packaging | Packaging Hall |  | 2024-10-17 15:25 | 2024-12-30 16:35 | Not Started | 0 | Assembly | 15 | 5
#WO431 | RTY256LP | Released | 13 | 13 | Ea | 10 | Blending | Blending-Hub |  | 2024-09-13 09:57 | 2024-10-17 09:57 | Not Started | 0 |  | 0.6 | 30
#WO431 | RTY256LP | Released | 13 | 13 | Ea | 20 | Packaging | Packaging Hall |  | 2024-09-15 08:51 | 2024-10-17 09:57 | Not Started | 0 | Blending | 0.6 | 30
#WO482 | LUM851 | Released | 6 | 6 | Ea | 10 | Assembly | Assembly-Hub |  | 2024-10-17 12:45 | 2024-11-17 12:45 | Not Started | 0 |  | 3 | 15
#WO611 | RTY256LP | In Process | 20 | 18 | Ea | 10 | Blending | Blending-Hub |  | 2024-09-22 10:57 | 2024-12-12 10:57 | In Progress | 2 |  | 0.6 | 30
#WO611 | RTY256LP | In Process | 20 | 20 | Ea | 20 | Cooling | Freezer |  | 2024-09-08 09:00 | 2024-12-12 10:57 | Not Started | 0 | Blending | 0.6 | 30
#WO611 | RTY256LP | In Process | 20 | 20 | Ea | 30 | Packaging | Packaging Hall |  | 2024-09-24 09:51 | 2024-12-12 10:57 | Not Started | 0 | Cooling | 0.6 | 30
#WO682 | IKO185E | Released | 4 | 4 | Ea | 10 | Assembly | Assembly-Hub |  | 2024-10-21 13:55 | 2024-12-08 09:57 | Not Started | 0 |  | 4 | 15
#WO682 | IKO185E | Released | 4 | 4 | Ea | 20 | Packaging | Packaging Hall |  | 2024-10-21 16:25 | 2024-12-08 09:57 | Not Started | 0 | Assembly | 15 | 5
#WO741 | RTY256LP | Released | 20 | 20 | Ea | 10 | Blending | Blending-Hub |  | 2024-10-14 11:13 | 2024-11-14 11:13 | Not Started | 0 |  | 0.6 | 30
#WO741 | RTY256LP | Released | 20 | 20 | Ea | 20 | Packaging | Packaging Hall |  | 2024-10-15 09:29 | 2024-11-14 11:13 | Not Started | 0 | Blending | 0.6 | 30
#WO872 | LUM851 | In Process | 1 | 1 | Ea | 10 | Assembly | Assembly-Hub |  | 2024-10-06 09:00 | 2024-10-15 11:13 | Not Started | 0 |  | 3 | 15
#WO921 | RTY256LP | Released | 16 | 16 | Ea | 10 | Blending | Blending-Hub |  | 2024-08-19 13:09 | 2024-11-08 13:09 | Not Started | 0 |  | 0.6 | 30
#WO921 | RTY256LP | Released | 16 | 16 | Ea | 20 | Packaging | Packaging Hall | Hall-C | 2024-08-21 14:27 | 2024-11-08 13:09 | Not Started | 0 | Blending | 0.6 | 30
#WO982 | IKO185E | Released | 6 | 6 | Ea | 10 | Assembly | Assembly-Hub |  | 2024-10-30 11:15 | 2024-11-30 11:15 | Not Started | 0 |  | 4 | 15
#WO982 | IKO185E | Released | 6 | 6 | Ea | 20 | Packaging | Packaging Hall |  | 2024-10-30 15:55 | 2024-11-30 11:15 | Not Started | 0 | Assembly | 15 | 5

## Work Center
Resource Name | Work Center Name | Work Center Type | Work Calendar | Labor Resources
B-Hub1 | Blending-Hub | Blender Center | SF Production Calendar | 1
Hall-A | Packaging Hall | Packaging Center | SF Production Calendar | 1
A-Corner1 | Assembly-Hub | Assembly Center | Default Work Calendar | 1
Freezer | Freezer | Freezer | Default Work Calendar | 1
B-Hub2 | Blending-Hub | Blender Center | Default Work Calendar | 1
Hall-B | Packaging Hall | Packaging Center | SF Production Calendar | 1
A-Corner2 | Assembly-Hub | Assembly Center | SF Production Calendar | 1
B-Hub3 | Blending-Hub | Blender Center | SF Production Calendar | 1
Hall-C | Packaging Hall | Packaging Center | SF Production Calendar | 1
A-Corner3 | Assembly-Hub | Assembly Center | SF Production Calendar | 1
Hall-D | Packaging Hall | Packaging Center | SF Production Calendar | 1
Hall-E | Packaging Hall | Packaging Center | SF Production Calendar | 1

## Work Calendar Assignment
Resource Name | From | Until | Work Calendar
B-Hub1 | 2019-01-01 08:00 | 2035-01-01 08:00 | Default Work Calendar
Hall-A | 2019-01-01 08:00 | 2035-01-01 08:00 | Default Work Calendar
A-Corner1 | 2019-01-01 08:00 | 2035-01-01 08:00 | Default Work Calendar
Freezer | 2019-01-01 08:00 | 2035-01-01 08:00 | LPT-Calendar
B-Hub2 | 2019-01-01 08:00 | 2035-01-01 08:00 | Default Work Calendar
Hall-B | 2019-01-01 08:00 | 2035-01-01 08:00 | Default Work Calendar
A-Corner2 | 2019-01-01 08:00 | 2035-01-01 08:00 | Default Work Calendar
B-Hub3 | 2019-01-01 08:00 | 2035-01-01 08:00 | Default Work Calendar
Hall-C | 2019-01-01 08:00 | 2035-01-01 08:00 | Default Work Calendar
A-Corner3 | 2019-01-01 08:00 | 2035-01-01 08:00 | Default Work Calendar
Hall-D | 2019-01-01 08:00 | 2035-01-01 08:00 | Default Work Calendar
Hall-E | 2019-01-01 08:00 | 2035-01-01 08:00 | Default Work Calendar

## Work Calendar
Internal ID | Name | Comments | Start Hour | Work Hours Per Day | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Break 1 Start | Break 1 End | Break 2 Start | Break 2 End
1 | Default Work Calendar |  | 9:00 | 8 | No | Yes | Yes | Yes | Yes | Yes | No | 13:00 | 13:30 | 15:30 | 15:45
2 | LPT-Calendar | Work Calendar for Long-Production-Time Items | 7:00 | 16 | No | Yes | Yes | Yes | Yes | Yes | No | 12:00 | 12:30 | 14:30 | 14:45