## Project Status Report
Project Status Report | [9 empty] | STATUS REPORTING LEGEND
Project Name: | [9 empty] | Overall Team Status
Project Overview: | [9 empty] | Green | On Target: You will hit all 'Must Hit' Milestone workplan dates
ROI: | [8 empty] | Status Key | Yellow | Off Track: Danger Range: There is a risk you will miss some 'Must Hit' Milestone dates and/or not complete everything by the projected end date
Business Owner(s): | [9 empty] | Red | Off Track 'Must Hit' Milestones and phase end activity dates will not be met
Target Completion Date:
Project Status Date: | [9 empty] | Individual Milestone Status
Overall Project Status (G, Y, R): | [9 empty] | Green | On Target: You will hit the milestone date listed in the workplan. all issues can be handled internally
Reason if Status is Yellow or Red: | [9 empty] | Yellow | Off Track: There is a risk the milestone will be not be complete by the workplan date
[10 empty] | Red | Off Track Milestone date will not be hit – the go-live date is jeopardized
Milestones
Milestone # | Description | Task Owner | Estimated Start Date | Estimated Completion Date | Actual Completion Date | % Complete | Status (G,Y,R) | Dependencies | Notes | Risk Management Severity Guide |  |  | Complete
1 | [9 empty] | Green | Risk Mitigated or No Impact: Risk has been mitigated or no potential impact from risk if risk occurs. |  | Green | Open
2 | [9 empty] | Yellow | Danger Range: Risk has potential to negatively impact the project. Solution to risk identified and is being actively worked. |  | Yellow | Closed
3 | [9 empty] | Red | Serious Issue: Risk has not been resolved and will impact project. No solution to risk has been identified. |  | Red | Pending Update
4 | [12 empty] | No Status | Monitoring
5
6
7 | [11 empty] | Business Owner
8 | [11 empty] | Executive Sponsor |  | 1. High
9 | [11 empty] | Other LOB |  | 2. Medium
10 | [11 empty] | PMO |  | 3. Low
11 | [11 empty] | Program Manager
12 | [11 empty] | Project Sponsor
13 | [11 empty] | Project Team
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
Key Accomplishments This Week (ONLY the Top 3 - 5)
Next Steps (ONLY the Top 3 - 5)
Issues & Escalations
Issue # | Description |  | Owner of Next Step | Due Date | Status | Escalation Level |  | Comments
Major Risks
Risk # | Description | Mitigation Strategy |  |  |  | Severity | Potential Timing |  | Status (Red/Yellow/Green)
Decisions Requiring Escalation
Decision |  | Business Impact |  | Rationale |  | Approved by | Communication Audience |  | Due Date
Change Control Log
Request Number | Change Request | Requested By | Date Requested | Business Driver and Impact | Cost Estimate (IT and Business) | Contingency Plan | Impact if Not Done |  | Status
Off track, progress in jeopardy
Off track, mitigation strategy/
action plan in place
On Target

## Status Report Instructions
The section at the top indicates the overall team status as green (on track), yellow (risk of missing deadlines), and red (significantly off track) in addition to key project details. The Milestone section tracks the status of the milestones for each subteam. The final section lists key accomplishments, upcoming tasks, issues, risks, and required decisions.
Instructions
1. Complete each of the top sections shaded in blue. These cells will need to be updated weekly to remain current.
2. Use drop down lists in cells where available.
3. If a status is Yellow or Red, please explain why and what is happening to mitigate the rating. Green ratings require no explanations.
4. Use the explanations listed below to complete your weekly status reports. If you have any questions, please contact your manager.
Column | Description
Milestones
Description | Critical objectives that need to be achieved by the project team
Task Owner | Person responsible for ensuring task is completed
Estimated Start Date | Date task is scheduled to start
Estimated Completion Date | Current estimated date for the completion of the milestone
Actual Completion Date | Actual date for the completion of the milestone
% Complete | Percentage of work completed toward the milestone
Status | Green = On Target (You will meet all 'Must Hit' milestone workplan dates) Yellow = Danger Range: There is a risk you will miss some 'Must Hit' Milestone dates and/or not complete everything by the projected end date Red = Off Target: Will miss multiple
Dependencies | Dependencies on other teams to complete the milestone
Notes
Key Accomplishments This Week (ONLY the Top 3 - 5) | List the top 3-5 accomplishments for the past week
To Do Next Week (ONLY the Top 3 - 5) | List the top 3-5 tasks to be performed next week
Issues & Escalations
Issue Number | Refer to a tracking number (if known). If Issue tracking number is not known, leave Issue Number blank.
Description | Describe the Risk in detail.
Owner of next Step | Who is responsible for resolving the issue?
Due Date | When does the particular issue need to be resolved?
Status | Select one: Open, Closed, Paused/Deferred, Pending Update, Monitoring
Escalation Level | Select one: PMO, Project Sponsor, Functional Owner, Cross Functional Team, Executive Steering Team, Team Leads
Comments | Provide additional comments if needed to define issue. If escalation assistance needed, you are responsible for escalating.
Major Risks
Risk Number | Refer to a tracking number (if known). If Risk tracking number is not known, leave Risk Number blank.
Description | Describe the Risk in detail.
Mitigation Strategy | How will the risk be addressed? What is the strategy to ensure the risk is properly mitigated? Who owns the mitigation strategy?
Severity | Select one: 1. High, 2. Medium, or 3. Low
Potential Timing | When should the identified risk need to be resolved?
Status | Green = Risk Mitigated or No Impact: Risk has been mitigated or no potential impact from risk if risk occurs. Yellow = Danger Range: Risk has potential to negatively impact the project. Solution to risk identified and is being actively worked. Red = Serious Issue: Risk has not been resolved and will impact project. No solution to risk has been identified.
Decisions Requiring Escalation
Decision | List decisions that need to be made
Business Impact | Describe the business impact of the decision
Rationale | Describe the rationale behind the decision
Endorsed By | List the people who have endorsed the decision
Communication Audience | To whom does the decision message need to be communicated?
Due Date | By what date does the decision need to be made?
Change Control Log
Change Request | Identify Change Request Name
Requested By | Identify who is requesting the change?
Date Requested | Date change request requested
Business Driver and Impact | What is the primary Business Driver for the change request and what impact will the change request have on the business?
Cost Estimate (IT and Business) | What is the total cost of implementing the change? Include Business and IT costs…
Contingency Plan | What is your plan if the change request is not approved?
Impact if Not Done | What will be the impact if change request is not approved?
Status | Use drop down list to identify current status of change request.

## Risk Management Plan
Risk Management Severity Guide
[5 empty] | Green | Risk Mitigated or No Impact: Risk has been mitigated or no potential impact from risk if risk occurs.
[5 empty] | Yellow | Danger Range: Risk has potential to negatively impact the project. Solution to risk identified and is being actively worked.
[5 empty] | Red | Serious Issue: Risk has not been resolved and will impact project. No solution to risk has been identified.
Risk Management Plan | [8 empty] | Green
Yellow
Red
Risk # | Risk Identification Method (how to identify risk) | Project Task | Threat Event | Probability / Impact | Mitigation Strategy | Escalation Strategy | Implemented / Responsibility | Status

## Issues Log
PMO
Project Sponsor
Open | Functional Owner | Issue
Closed | Cross Functional Team | Action
Pending Update | Executive Steering Committee
Paused/Deferred | Team Leads
Monitoring
Issues Log
Issue No. | Status | Severity | Escalation Level | Creation Date | Description | Next Step | Owner of Next Step | Follow up Date | Resolution/Notes
Open
Monitoring
Tracking Only
Closed
Status Legend: | Closed | Pending Update | High priority and over due
Severity: | - High: Immediate or significant impact on people, costs, premiums, Day 1, or legal (anti-trust) risk
Legend | - Medium: Moderate impact on people, costs, premium, Day 1, or legal (anti-trust) risk
-Low: Low impact on people, costs, premiums, Day 1, or legal (anti-trust) risk
Workstream
01. Weekly Status Report
02. eLMD
03. Salvage
04. Subrogation
05. Claims Vendor Contracts
06. Cash Receipting
07. EC Claims
08. Human Resources
09. Procurement
10. Real Estate
11. Print Fulfillment
12. Training
13. Licensing
14. Winscribe
15. Staff Counsel Identity
16. Claims Compliance
17. Field APD
18. CAT (Auto Response Team)
19. Vehicle Direct Repair
20. ServicePower (including Dispatch)
21. Field Liability
22. Complex Liability Claims
23. Coverage Verification Team
24. Glass Claims Processing
25. Towing Claims Processing
26. Non-Injury Liability Assessment
27. Desk Handled Auto Claims
28. Total Loss Settlement
29. First Notice of Loss
30. National Document and Imaging Center
31. Customer Service Surveys and Complaints
32. Facilities and Telecom
33. Claims Specialized Services
34. National Process Development Team
35. National Process Audit Team
36. Commercial Liability
37. Work Comp
38. Litigation Management
39. Staff Legal
40. Claims User Resource
41. Reporting COE
42. Fleet and Cell Phones
43. Claims Communication & Creative Services
44. Med/PIP
45. Quality Assurance
46. Records Management
47. SIU
48. Vendor Management
49. PMO
50. Claims Finance
51. IT (Helpdesk, Hotswap, Asset Mgmt, ID Admin)
52. IT (Claims Platform, Internet & Print Fulfillment)
53. Boat, RV, Motorcycle and ATV
54. IT (Infrastructure)
55. Telecom
56. Self Service
57. Agency Auto