## Slide 1
Data Strategy
Roadmap
Template

## Slide 2: Roadmap Structure
  Design Data Pipelines
  Build Phase 1 Sources
  Build Phase 2 Sources
  Design ML Ops
  Build ML Ops
  ID / Hire Analytic Thought Leader
  Empower / Enable Data Analyst
  Build Operations Data Team
  Advanced Analytics Use Case Prioritization
The projects on the roadmap are broken into five major categories, each containing sub-activities which will be outlined in the following slides.
Software
Talent
  Cloud Selection Process
  DB Setup / Procured
  User Tooling
  Security
Infrastructure
  Develop Operational Model for Data Monetization
  Establish Data Governance Charter
  Kick off Data Governance Committee
  Prioritize / Fund / Monitor Work
Data Governance
Delivery Management
  Provide project governance and management across projects and initiatives

## Slide 3: One Year Roadmap
Infrastructure
Software
Talent
Data Governance
Delivery Management
Q1 2025
Q2 2025
Q3 2025
Q4 2025
($XXX-$XXX)
($XXX-$XXX)
($XXX-$XXX)
($XXX-$XXX)
  ID / Hire Analytic Thought Leader
TA 1
  Advanced Analytics Use Case Prioritization
TA 4
SW 1
  Design Data Pipelines
  Build Phase 1 Sources
SW 2
TA 2
  Empower / Enable Data Analyst
  Develop Operational Model for Data Monetization
DG 1
Ne business
  Build Phase 2 Sources
SW 3
  Establish Data Governance Charter
DG 2
  Design ML Ops
SW 4
TA 3
  Build Operations Data Team
DG 3
  Kick off Data Governance Committee
DB Setup / Procured
IF 2
IF 1
  Cloud Selection Process
  User Tooling
IF 3
DM1
  Provide project governance and management across projects and initiatives
Client Led Project
Partner Led Project
Project Dependency
  Security
IF 4
  Build ML Ops
SW 5
DG 4
  Prioritize / Fund / Monitor Work

## Slide 4: Software Initiative 3: Build Phase 2 Sources
Deploy Databricks to “Client” leveraging existing AWS S3 assets. Provide a unified Data Lakehouse environment to expose data throughout the organization to speed development of analytic products.
Databricks provides an industry leading data platform as a service. Leveraging already owned cloud data storage, it provides organizations with compute resources and a powerful suite of tools to enable data analytics in a collaborative environment.
The initial goals will be to develop necessary frameworks and support structure to facilitate security and operations in Databricks and expose the data assets produced by the “Client” project.
2-4 Weeks: Procure and deploy Databricks on clients AWS instance
6-10 Weeks: Work under client guidance to build workflows and frameworks to support ongoing operations and compliance needs
8-12 Weeks: Develop views to the “Client” data modeled after views available in the Data Mart
Improved tooling that creates leverage and reduces support efforts
Platform that supports broad integration of data
Enables machine learning and other advanced analytics
SUMMARY
DESCRIPTION
TASKS
Concurrent Activities
BENEFITS / CAPABILITIES
SW 3
Start: Q3-2025
Quick Win Placing Hasura on top of the existing v4 database could create an immediately available API
Estimated Cost $X - $Y
Team Thoughts
One Senior Consultant
One Consultant
1
1

## Slide 5
Partner with UDig to Create Your Data Strategy
Let's Talk
Building a winning data roadmap doesn’t have to be a daunting, painstaking process. Contact us and let our data strategists help you identify the best path forward for your business.