## Dashboard & Instructions
Volve Tender Contract Review Checklist
Empowering Contractors with AI-Driven Insights
Built to work across different construction contracts. Focuses on outcomes (risk, remedy, caps), not clause numbering.
1 | Navigate to the 'Contract Clause Review' tab
2 | For each clause category, review the provided expert guidance
3 | Fill in the 'Contract Section/Ref' and 'Current Wording' with details from your tender document
4 | Select the 'Risk Level' (Low, Medium, High) and 'Review Status' (Not Started, In Review, Negotiated, Approved) using the dropdowns
5 | Document your 'Action Plan' based on the 'Mitigation Action' and your specific contract
6 | The 'Risk Level' column will automatically highlight based on your selection
7 | Leverage the 'Volve AI Edge' column to understand how Volve automates and simplifies this process
8 | Tailor the "What to Look For (Red Flags)", "Suggested Position", "Action Plan" to your company internal practices
Automate your tender review and mitigate risks with Volve AI!
Disclaimer: This checklist is general information to help spot commercial contract risks and prepare negotiation points. It is not legal advice and isn’t tailored to any project, contract form, or jurisdiction. You should get qualified legal and commercial advice before acting on it.
How to Use This Tool
Visit volvetech.com to learn more and book a demo >

## Contract Clause Review
Clause Category | Review Question | What to Look For (Red Flags) | Current Wording | Risk Level | Review Status | Suggested Position | Contract Section/Ref | Action Plan
Extension of Time (EOT) | Does the contract provide a fair process for claiming time extensions for excusable, unforeseen delays? | • Very short notice periods and strict time bars (e.g., <7 days) • Grounds for EOT unclear or too narrow • EOT allowed but delay costs barred even for client-caused delay • Unworkable substantiation burden (daily notices, excessive detail) | [Paste clause text] |  | Not Started | Preferred: EOT for delays beyond contractor control (incl. client-caused delay and variations), with reasonable notice periods and no automatic forfeiture where there’s no prejudice. Fallback: If strict time bars remain, add relief where the client is aware of the delay and allow late notice unless prejudice is proven. | [Section / page / clause ref] | Selection: Amend. - Next step: Propose clearer EOT grounds and notice wording. Add cost entitlement for client-caused delay where appropriate. - If rejected: Qualify with tender clarification on notice relief and dependencies. - Price: Prelims/prolongation allowance if cost entitlement remains barred. - Escalate: If time bars are conditions precedent.
Ground Conditions | Does the contract fairly allocate the risk of unforeseen ground conditions, or does the contractor bear all the risk? | • “Inspected and accepts all conditions” disclaimers • No relief for unknown utilities/obstructions/contamination • No right to rely on provided surveys/reports • Time-only remedy (no cost) | [Paste clause text] |  | Not Started | Preferred: Relief for materially different site conditions compared to provided information or what was reasonably foreseeable, with time and cost adjustments. Fallback: At minimum, time relief plus defined valuation method (rates/dayworks) and agreed thresholds for compensation. | [Section / page / clause ref] | Selection: Amend. - Next step: Insert Differing Site Conditions (DSC) relief (time + cost) and reliance on employer information. - If rejected: Qualify with explicit exclusions/assumptions. - Price: Add a defined contingency if risk remains unpriced. - Escalate: If broad “accept all conditions” disclaimers remain.
Limitation of Liability | Is your financial liability capped at a reasonable level, or are you exposed to unlimited/uncertain risk? | • No cap, or cap that’s easy to bypass • Broad carve-outs that effectively make liability uncapped (delay, indemnities, IP, confidentiality, etc.) • No exclusion/limit for indirect/consequential loss (where permitted) • Cap not aligned with insurance | [Paste clause text] |  | Not Started | Preferred: Aggregate cap aligned to contract value and available insurance. Keep carve-outs narrow and insurable. Exclude indirect/consequential loss where permitted and appropriate. Fallback: Higher cap for specific heads but retain an overall backstop cap and tightly defined carve-outs. | [Section / page / clause ref] | Selection: Amend. - Next step: Propose cap + clarify scope (aggregate/per claim) + narrow carve-outs. - If rejected: Qualify and Escalate for internal approval. - Price: Only if residual exposure is measurable and insurable.
Liquidated Damages (LDs) | Are delay damages structured fairly, capped, and aligned with the programme and dependencies? | • High LD rate with no overall cap • LDs apply despite client-caused delay / late access / late info • LDs plus general damages for same delay exposure • Sectional completion unclear or overly broad | [Paste clause text] |  | Not Started | Preferred: Delay damages as the agreed remedy for delay, capped, and not applicable to client-caused delay. Clear triggers (incl. sectional completion definitions where used). Fallback: If sole-remedy is rejected, cap overall delay exposure and add clear carve-outs for client-caused delay and key dependencies. | [Section / page / clause ref] | Selection: Amend. - Next step: Add LD cap and prevention/dependency carve-outs. - If rejected: Qualify (dependencies + access dates). - Price: Allowance for LD exposure if uncapped/unclear. - Escalate if LDs are uncapped or overlap with general damages.
On-Demand Bonds | Can the client call the bond without objective trigger, notice, cure period, or expiry/step-down? | • “On demand/on first demand/unconditional” • No notice/cure prior to call • No expiry/sunset or step-down • Call allowed for disputed amounts | [Paste clause text] |  | Not Started | Preferred: Conditional call requirements (notice, cure, objective trigger) plus expiry and step-down aligned to completion/taking over. Fallback: If on-demand is required, add sunset + step-down and limit calls to certified/undisputed amounts or defined events. | [Section / page / clause ref] | Selection: Amend. - Next step: Propose conditionality plus sunset and step-down. - If rejected: Escalate for approval. - Price: Bank/bond costs and cashflow impact.
Risk & Liability Allocation (Indemnities) | Does the contract require indemnities for risks outside contractor control or beyond insurability? | • Broad “indemnify and hold harmless” beyond fault/control • Indemnity for employer design, third-party negligence, or undefined categories • Uninsurable indemnities (pure economic loss, broad IP without limits, etc.) | [Paste clause text] |  | Not Started | Preferred: Indemnities limited to losses caused by contractor breach/negligence and within contractor control, aligned to insurance. Fallback: If broader indemnities remain, cap them, narrow triggers, and add carve-outs for employer/third party acts plus indirect loss limits where permitted. | [Section / page / clause ref] | Selection: Amend. - Next step: Narrow indemnity scope and add caps/carve-outs. - If rejected: Escalate and consider Qualify with specific exclusions. - Price: Only if exposure is quantifiable and insurable.
Acceleration & Compensation | If asked to accelerate, is there a clear process and entitlement to recover acceleration costs? | • Obligation to accelerate without written instruction • No method to price acceleration or assess time impact • Acceleration implied through programme pressure without compensation route | [Paste clause text] |  | Not Started | Preferred: Acceleration only by written instruction, with agreed compensation method and time impact handled transparently. Fallback: Pre-agree rates/dayworks and a method for measuring disruption/prolongation where acceleration is requested or effectively required. | [Section / page / clause ref] | Selection: Amend. - Next step: Add written instruction requirement and valuation mechanism before acceleration. - If rejected: Qualify “no acceleration without written instruction”. - Price: Only limited allowances with clear triggers.
Back-to-Back (Subcontracts) | Are subcontract obligations aligned with the main contract so you can comply without being caught in the middle? | • Notice periods misaligned (sub longer than main) • Dispute routes inconsistent • Payment linked to upstream payment (often restricted/regulated in some markets) • Flow-down obligations impractical to administer | [Paste clause text] |  | Not Started | Preferred: Subcontracts aligned to key main-contract obligations, with shorter notice periods than the main contract and harmonised dispute/admin routes. Payment mechanism compliant with local rules. Fallback: Where perfect alignment isn’t possible, carve-outs plus internal controls (notice tracker, early warnings, approvals). | [Section / page / clause ref] | Selection: Qualify. - Next step: Confirm ability to flow down and administer obligations. - If misalignment creates liability exposure, Amend relevant main terms or Escalate. - Price: Only after mapping key notice and payment mechanics.
Complete Scope | Does the contract make you responsible for work not explicitly shown/described, without boundaries and precedence rules? | • “All work necessary for completion” without limits • No clear order of precedence (drawings vs specs vs schedules) • Contractor must verify/complete employer design without control | [Paste clause text] |  | Not Started | Preferred: Clear scope boundaries, exclusions, and document hierarchy. Implied work limited to what is reasonably inferable within the agreed scope and information provided. Fallback: If broad scope phrases remain, convert assumptions/clarifications into contract documents and price identified gaps explicitly. | [Section / page / clause ref] | Selection: Amend. - Next step: Add precedence clause and scope boundary language. - If rejected: Qualify with explicit exclusions/assumptions. - Price measurable allowances. Escalate if scope becomes effectively unlimited.
Fitness for Purpose | Are you warranting a specific outcome (often uninsurable), vs a skill-and-care obligation with defined performance tests? | • “Fitness for purpose” wording • Performance guarantees without defined tests/tolerances/dependencies • Obligations depend on employer inputs but still sit on contractor | [Paste clause text] |  | Not Started | Preferred: Skill and care standard, with only specific, measurable performance commitments where tests and employer dependencies are defined and priced. Fallback: If fitness remains for limited items, tie to defined metrics/tests/dependencies and cap exposure (and align with insurance). | [Section / page / clause ref] | Selection: Amend. - Next step: Replace broad FFP language and define any performance regime. - If rejected: Escalate (insurance check) and consider Qualify + Price only if measurable and insurable.
No-Damages-for-Delay | Does the contract bar cost recovery for delays/disruption even when client-caused? | • Blanket waiver of delay/disruption costs • Time-only relief for employer-caused delay/suspension/late access • No valuation mechanism for prolongation/disruption | [Paste clause text] |  | Not Started | Preferred: Allow cost recovery for client-caused delay/disruption and instructed change, with a defined valuation method. Fallback: If a cost bar remains, carve out defined employer risk events (late access/info, suspension, instructed change) and include a prelims/prolongation mechanism. | [Section / page / clause ref] | Selection: Amend. - Next step: Add carve-outs and valuation route. - If rejected: Qualify key dependencies. - Price: Prelims/disruption risk with escalation for approval.
Pay-When / If-Paid | Is payment contingent on upstream payment or otherwise unpredictable, putting cashflow at risk? | • Condition-precedent language tying payment to upstream payment (often restricted/regulated in construction markets) • Long payment periods + broad set-off • Unclear certification and pay-less mechanism | [Paste clause text] |  | Not Started | Preferred: Payment dates and certification mechanics independent of upstream payment, with clear set-off/pay-less rules and predictable cashflow. Fallback: If any linkage is insisted on, restrict to narrow insolvency scenarios and define process and time limits. | [Section / page / clause ref] | Selection: Amend. - Next step: Remove/limit upstream conditions and tighten payment mechanics. - If rejected: Escalate and Qualify. - Price: Only with clear, bounded cashflow impact.
Termination Settlement | If terminated, will you be compensated for work done and committed costs (incl. demob, subcontract liabilities, materials on/off-site)? | • No demobilisation/cancellation costs • No recovery for off-site materials/plant • Settlement excludes OH&P or defined heads • Client can value at discretion | [Paste clause text] |  | Not Started | Preferred: On termination, pay for work executed, committed costs, demob, subcontract liabilities, and fair OH&P, with a clear valuation basis and evidence process. Fallback: If OH&P/profit is resisted, ensure recovery of committed costs, cancellation charges, and a defined demob allowance. | [Section / page / clause ref] | Selection: Amend. - Next step: Define settlement heads and valuation method. - If rejected: Escalate and Qualify (materials/plant ownership, cancellation costs). - Price: Only if exposure is quantifiable.
Termination for Convenience | Can the client terminate without cause, leaving contractor exposed to unrecovered costs and margin? | • Immediate/short notice convenience termination • No termination fee or margin on committed work • No protection for procurement commitments and subcontract termination costs | [Paste clause text] |  | Not Started | Preferred: Convenience termination only with reasonable notice and a defined settlement including committed costs, demob, and a defined termination fee/margin on committed scope. Fallback: If margin is resisted, secure recovery of committed costs, cancellation liabilities, and a defined demob allowance, with clear process/timeline. | [Section / page / clause ref] | Selection: Amend. - Next step: Add notice + defined settlement/fee. - If rejected: Escalate and Qualify procurement commitments. - Price: Only after bounding exposure and confirming insurability/cashflow impact.
Variations / Change Control | Does the contract set a workable process for instructing, valuing, and time-adjusting changes, so you’re not forced to proceed at risk? | • Client can instruct changes informally (or “deemed instruction”) but no clear entitlement to time/cost • Contractor must proceed before valuation is agreed, with no interim payment mechanism • Valuation basis unclear (no rates, no dayworks rules, no prelims/OH&P rules) • Time impact decided unilaterally by the client/PM • Tight notice/time bar for variations or claims • Changes to completion dates without EOT logic | [Paste clause text] |  | Not Started | Preferred: Changes only by written instruction (with sensible emergency carve-out). Clear valuation basis (rates/dayworks, prelims, OH&P) and entitlement to both time and cost where change impacts programme/resources. Time impact assessed promptly and agreed or determined under a defined mechanism. Fallback: If prior written instruction isn’t accepted, allow “confirmed instruction” within a short period and protect payment/time from the date the change is directed. If valuation can’t be agreed, provide interim payment and later true-up under defined rules. | [Section / page / clause ref] | Selection: Amend. - Next step: Insert clear instruction + valuation + time-impact mechanism. Add interim valuation/true-up if agreement lags. - If rejected: Qualify with tender clarifications (no change without compensation and time adjustment) - Price: Only where exposure can be bounded. - Escalate: If changes can be directed without a route to time and money.
Payment & Retention Mechanics | Do the payment provisions provide predictable cashflow, clear certification, and fair set-off rules (including retention), consistent with local construction payment regulation? | • Long payment cycle (application-to-payment) or vague milestone triggers • Certification at client discretion or no deemed certification • Broad unilateral set-off rights without notice or linkage to certified sums • Ambiguous pay-less / withholding process (or very short notice) • Retention high, release tied to distant events, or release conditions unclear • Final account timing open-ended, allowing prolonged underpayment • Interest/suspension rights absent or heavily limited | [Paste clause text] |  | Not Started | Preferred: Clear payment cycle (application, certification, payment dates) with objective certification criteria and a defined process for pay-less/withholding and set-off. Retention % and release timing defined (split at completion and end of defects, or equivalent). Final account timetable and dispute route defined. Payment mechanics reviewed against applicable local payment rules for construction contracts. Fallback: If long cycles remain, tighten certification and pay-less mechanics, require notice and substantiation for set-off, and define retention release milestones. Add interest on late payment and a right to suspend for non-payment where permitted. | [Section / page / clause ref] | Selection: Amend. - Next step: Tighten payment timetable, certification rules, and set-off/pay-less mechanics. Define retention release milestones and final account timetable. - If rejected: Escalate (cashflow and regulatory risk) and qualify tender assumptions (payment cycle, retention release). - Price: Model cashflow impact and any security/financing costs.

## Volve Feature Guide
Unlock Advanced Contract Analysis with Volve AI
Manual Contract Review vs. Volve AI
Feature | Manual Review | Volve AI
Clause Identification | Time-consuming, prone to human error, requires legal expertise. | Instant, AI-powered identification of all critical clauses.
Risk Assessment | Subjective, inconsistent, relies on individual experience. | Objective, consistent risk flagging based on industry best practices.
Compliance Tracking | Manual checklists, difficult to audit, easily overlooked. | Automated tracking, audit trails, real-time compliance status.
Decision Support | Relies on memory and fragmented notes. | Contextual insights, mitigation strategies, and actionable recommendations.
Efficiency | Slow, costly, diverts resources from core activities. | Rapid, cost-effective, frees up legal and project teams.
Ready to transform your tender process?
Book a personalised demo of Volve AI today >