## Setup
HALLORAN CONSTRUCTION CO.
Riverside Master Suite Addition
Project Setup
FIELD | VALUE
Project Name | Riverside Master Suite Addition
Project Number | 2026-014
Owner | Brian & Megan Smith
Project Address | 1247 Oakwood Drive, Atlanta GA 30309
Contract Value | 185000
Start Date | 2026-01-15
Target Completion | 2026-05-30
Notes
Inputs are blue. Edit only the yellow cells. The other tabs reference these values.

## Budget
HALLORAN CONSTRUCTION CO.
Riverside Master Suite Addition
Project Budget
COST BREAKDOWN | [5 empty] | CATEGORIES
TYPE | CATEGORY | DESCRIPTION | BUDGET | CO FLAG | CODE | TOTAL BUDGET
◯ | Labor | Labor | 46700 |  | 01-000 | Labor
◆ | Labor | Site supervisor (16 weeks) | 24000 |  | 01-001 | Materials
◆ | Labor | Carpentry crew | 18500 |  | 01-002 | Subcontractors
◆ | Labor | Cleanup / general labor | 4200 |  | 01-003 | Equipment
◯ | Materials | Materials | 41200 |  | 02-000 | Overhead
◆ | Materials | Lumber package | 14800 |  | 02-001
◆ | Materials | Roofing materials | 6200 |  | 02-002
◆ | Materials | Windows and exterior doors | 8400 |  | 02-003
◆ | Materials | Drywall and interior finishes | 5600 |  | 02-004
◆ | Materials | Trim and millwork | 3800 |  | 02-005
◯ | Subcontractors | Subcontractors | 45050 |  | 03-000 | TOTAL BUDGET | Amount
◆ | Subcontractors | Foundation / concrete sub | 12500 |  | 03-001
◆ | Subcontractors | Electrical sub | 9800 |  | 03-002 | Original Budget (excl. COs) | 145250
◆ | Subcontractors | Plumbing sub | 7400 |  | 03-003 | Approved Change Orders | 4500
◆ | Subcontractors | HVAC sub | 8900 |  | 03-004 | Revised Contract Value | 149750
◆ | Subcontractors | Painting sub | 4600 |  | 03-005
◯ | Equipment | Equipment | 5800 |  | 04-000
◆ | Equipment | Excavator rental | 2800 |  | 04-001
◆ | Equipment | Scaffolding rental | 1200 |  | 04-002
◆ | Equipment | Dumpster (3 hauls) | 1800 |  | 04-003
◯ | Overhead | Overhead | 10750 |  | 05-000
◆ | Overhead | Permits and inspection fees | 1850 |  | 05-001
◆ | Overhead | Insurance allocation | 2400 |  | 05-002
◆ | Overhead | Project management overhead | 6500 |  | 05-003
◆ | Materials | CO #1: Upgraded kitchen window package | 2500 | CO | 05-004
◆ | Subcontractors | CO #2: Add bathroom plumbing rough | 2000 | CO | 05-005

## Actual
HALLORAN CONSTRUCTION CO.
Riverside Master Suite Addition
Project Actuals | [6 empty] | Notes
Inputs are blue. The Category and Description will auto-populate based on the Code selected.
ACTUAL COST LOG | [6 empty] | BUDGET CODE REFERENCE
DATE | CODE | CATEGORY | DESCRIPTION | VENDOR / PAYEE | AMOUNT |  | CODE | CATEGORY | DESCRIPTION
2026-01-01 | 05-001 | Permits and inspection fees |  | City of Atlanta Permits | 1850 | ◯ | Labor | Labor
2026-01-03 | 05-002 | Insurance allocation |  | Hartford Insurance | 600 | ◆ | Labor | Site supervisor (16 weeks)
2026-01-06 | 05-003 | Project management overhead |  | Halloran Construction | 1200 | ◆ | Labor | Carpentry crew
2026-01-08 | 04-001 | Excavator rental |  | United Rentals | 1400 | ◆ | Labor | Cleanup / general labor
2026-01-10 | 03-001 | Foundation / concrete sub |  | Patterson Concrete | 6000 | ◯ | Materials | Materials
2026-01-13 | 01-001 | Site supervisor (16 weeks) |  | Payroll | 1500 | ◆ | Materials | Lumber package
2026-01-16 | 04-003 | Dumpster (3 hauls) |  | Waste Pro | 400 | ◆ | Materials | Roofing materials
2026-01-20 | 03-001 | Foundation / concrete sub |  | Patterson Concrete | 6500 | ◆ | Materials | Windows and exterior doors
2026-01-22 | 01-001 | Site supervisor (16 weeks) |  | Payroll | 1500 | ◆ | Materials | Drywall and interior finishes
2026-01-23 | 04-001 | Excavator rental |  | United Rentals | 1400 | ◆ | Materials | Trim and millwork
2026-01-27 | 02-001 | Lumber package |  | 84 Lumber | 14800 | ◯ | Subcontractors | Subcontractors
2026-01-29 | 01-001 | Site supervisor (16 weeks) |  | Payroll | 1500 | ◆ | Subcontractors | Foundation / concrete sub
2026-01-30 | 01-002 | Carpentry crew |  | Payroll | 3500 | ◆ | Subcontractors | Electrical sub
2026-02-02 | 01-002 | Carpentry crew |  | Payroll | 3500 | ◆ | Subcontractors | Plumbing sub
2026-02-05 | 05-003 | Project management overhead |  | Halloran Construction | 1200 | ◆ | Subcontractors | HVAC sub
2026-02-06 | 01-001 | Site supervisor (16 weeks) |  | Payroll | 1500 | ◆ | Subcontractors | Painting sub
2026-02-10 | 02-002 | Roofing materials |  | ABC Supply | 4200 | ◯ | Equipment | Equipment
2026-02-12 | 01-001 | Site supervisor (16 weeks) |  | Payroll | 1500 | ◆ | Equipment | Excavator rental
2026-02-13 | 01-002 | Carpentry crew |  | Payroll | 3500 | ◆ | Equipment | Scaffolding rental
2026-02-17 | 02-002 | Roofing materials |  | ABC Supply | 2300 | ◆ | Equipment | Dumpster (3 hauls)
2026-02-19 | 02-003 | Windows and exterior doors |  | Pella Direct | 8400 | ◯ | Overhead | Overhead
2026-02-20 | 01-001 | Site supervisor (16 weeks) |  | Payroll | 1500 | ◆ | Overhead | Permits and inspection fees
2026-02-22 | 04-003 | Dumpster (3 hauls) |  | Waste Pro | 400 | ◆ | Overhead | Insurance allocation
2026-02-26 | 03-002 | Electrical sub |  | Voltage Electric | 4200 | ◆ | Overhead | Project management overhead
2026-02-27 | 01-001 | Site supervisor (16 weeks) |  | Payroll | 1500 | ◆ | Materials | CO #1: Upgraded kitchen window package
2026-03-01 | 03-003 | Plumbing sub |  | Reliable Plumbing | 3200 | ◆ | Subcontractors | CO #2: Add bathroom plumbing rough
2026-03-04 | 03-004 | HVAC sub |  | Comfort Systems HVAC | 4000
2026-03-05 | 01-001 | Site supervisor (16 weeks) |  | Payroll | 1500
2026-03-06 | 01-002 | Carpentry crew |  | Payroll | 3700
2026-03-09 | 05-002 | Insurance allocation |  | Hartford Insurance | 600
2026-03-10 | 05-003 | Project management overhead |  | Halloran Construction | 1200
2026-03-12 | 03-002 | Electrical sub |  | Voltage Electric | 2800
2026-03-14 | 03-003 | Plumbing sub |  | Reliable Plumbing | 2300
2026-03-16 | 01-001 | Site supervisor (16 weeks) |  | Payroll | 1500
2026-03-18 | 05-004 | CO #1: Upgraded kitchen window package |  | Pella Direct | 2400
2026-03-19 | 05-005 | CO #2: Add bathroom plumbing rough |  | Reliable Plumbing | 1850
2026-03-22 | 03-004 | HVAC sub |  | Comfort Systems HVAC | 2500
2026-03-23 | 01-001 | Site supervisor (16 weeks) |  | Payroll | 1500
2026-03-27 | 02-004 | Drywall and interior finishes |  | Sherwin-Williams | 2200
2026-03-29 | 01-003 | Cleanup / general labor |  | Payroll | 1200
2026-03-30 | 01-001 | Site supervisor (16 weeks) |  | Payroll | 1500
2026-04-03 | 02-004 | Drywall and interior finishes |  | Sherwin-Williams | 2000
2026-04-05 | 01-003 | Cleanup / general labor |  | Payroll | 1200
2026-04-08 | 01-001 | Site supervisor (16 weeks) |  | Payroll | 1500
2026-04-10 | 04-003 | Dumpster (3 hauls) |  | Waste Pro | 400
2026-04-13 | 05-002 | Insurance allocation |  | Hartford Insurance | 600
2026-04-16 | 05-003 | Project management overhead |  | Halloran Construction | 1200
2026-04-18 | 04-002 | Scaffolding rental |  | United Rentals | 900
2026-04-21 | 01-001 | Site supervisor (16 weeks) |  | Payroll | 1500

## Dashboard
HALLORAN CONSTRUCTION CO.
Riverside Master Suite Addition | [6 empty] | PROJECT COMPLETED
Budget vs. Actual Report | [6 empty] | 80%
PROJECT NO. |  |  | TARGET COMPLETION |  |  |  | STATUS
2026-014 |  |  | 2026-05-30 |  |  |  | In Progress
CONTRACT VALUE |  |  |  | ACTUAL COST TO DATE
189500 |  |  |  | 114850
Original contract: $185,000 |  |  |  | 76.7% of budget spent
CHANGE ORDER VALUE |  | REMAINING BUDGET |  | MARGIN ($) |  | MARGIN (%)
4500 |  | 34900 |  | 39750 |  | 20.98%
2 Change Orders |  | +23.3% of Total Cost Budget |  | Matches original estimate |  | on $189,500 revenue
COST VS PROGRESS
| COST BUDGET CONSUMED | 76.69% | ████████████████████████████████████████████░░░░░░░░░░░░░░
| PROJECT COMPLETED | 80% | ██████████████████████████████████████████████░░░░░░░░░░░░
Tracking 3 percentage points under project progress
CONTRACT REVENUE
DESCRIPTION | [6 empty] | AMOUNT
Original Contract | [6 empty] | 185000
CO 1 — CO #1: Upgraded kitchen window package | [6 empty] | 2500
CO 2 — CO #2: Add bathroom plumbing rough | [6 empty] | 2000
REVISED CONTRACT VALUE | [6 empty] | 189500
COST BREAKDOWN
CATEGORY / LINE ITEM |  |  |  | BUDGET | ACTUAL | % COMPLETE | REMAINING
LABOR |  |  |  | 46700 | 36100 | 77.3% | 10600
Site supervisor (16 weeks) |  |  |  | 24000 | 19500 | 81.25% | 4500
Carpentry crew |  |  |  | 18500 | 14200 | 76.76% | 4300
Cleanup / general labor |  |  |  | 4200 | 2400 | 57.14% | 1800
MATERIALS |  |  |  | 38800 | 33900 | 87.37% | 4900
Lumber package |  |  |  | 14800 | 14800 | 100% | 0
Roofing materials |  |  |  | 6200 | 6500 | 104.8% | -300
Windows and exterior doors |  |  |  | 8400 | 8400 | 100% | 0
Drywall and interior finishes |  |  |  | 5600 | 4200 | 75% | 1400
Trim and millwork |  |  |  | 3800 | 0 | 0% | 3800
SUBCONTRACTORS |  |  |  | 43200 | 31500 | 72.92% | 11700
Foundation / concrete sub |  |  |  | 12500 | 12500 | 100% | 0
Electrical sub |  |  |  | 9800 | 7000 | 71.43% | 2800
Plumbing sub |  |  |  | 7400 | 5500 | 74.32% | 1900
HVAC sub |  |  |  | 8900 | 6500 | 73.03% | 2400
Painting sub |  |  |  | 4600 | 0 | 0% | 4600
EQUIPMENT |  |  |  | 5800 | 4900 | 84.48% | 900
Excavator rental |  |  |  | 2800 | 2800 | 100% | 0
Scaffolding rental |  |  |  | 1200 | 900 | 75% | 300
Dumpster (3 hauls) |  |  |  | 1800 | 1200 | 66.67% | 600
OVERHEAD |  |  |  | 10750 | 8450 | 78.6% | 2300
Permits and inspection fees |  |  |  | 1850 | 1850 | 100% | 0
Insurance allocation |  |  |  | 2400 | 1800 | 75% | 600
Project management overhead |  |  |  | 6500 | 4800 | 73.85% | 1700
TOTAL PROJECT COST |  |  |  | 145250 | 114850 | 79.07% | 30400

## Calculations
CALCULATIONS — Single Stream Engine
Category metadata | [6 empty] | Budget Consumed Scale
POS | CATEGORY | DETAIL_COUNT | BLOCK_SIZE | BLOCK_START | BLOCK_END |  | 58
1 | Labor | 3 | 4 | 1 | 4 |  | Revised Cost Budget
2 | Materials | 5 | 6 | 5 | 10 |  | 149750
3 | Subcontractors | 5 | 6 | 11 | 16 |  | Original Cost Budget
4 | Equipment | 3 | 4 | 17 | 20 |  | 145250
5 | Overhead | 3 | 4 | 21 | 24
6 |  | 0 | 0
7 |  | 0 | 0
8 |  | 0 | 0
9 |  | 0 | 0
CO metadata
CO_IDX | ABS_ROW | EXISTS | CODE | DESC | AMOUNT | DISPLAY_LABEL
1 | 33 | TRUE | 05-004 | CO #1: Upgraded kitchen window package | 2500 | CO 1 — CO #1: Upgraded kitchen window package
2 | 34 | TRUE | 05-005 | CO #2: Add bathroom plumbing rough | 2000 | CO 2 — CO #2: Add bathroom plumbing rough
3 |  | FALSE
4 |  | FALSE
5 |  | FALSE
6 |  | FALSE
7 |  | FALSE
8 |  | FALSE
9 |  | FALSE
10 |  | FALSE
11 |  | FALSE
12 |  | FALSE
13 |  | FALSE
14 |  | FALSE
15 |  | FALSE
16 |  | FALSE
17 |  | FALSE
18 |  | FALSE
19 |  | FALSE
20 |  | FALSE
Section row markers
CO_COUNT | 2
SUM_BLOCK_SIZE | 24
CR_HEADER_ROW | 1
CR_SUBHEADER_ROW | 2
ORIG_CONTRACT_ROW | 3
FIRST_CO_ROW | 4
REVISED_CONTRACT_ROW | 6
SPACER_ROW | 7
CB_HEADER_ROW | 8
CB_SUBHEADER_ROW | 9
CB_FIRST_DATA_ROW | 10
TOTAL_PROJECT_COST_ROW | 34
END_ROW | 34
UNIFIED STREAM
ROW_ID | KIND | LABEL | BUDGET | ACTUAL | PCT | VARIANCE | VARIANCE | _section | _co_idx | _cb_pos | _pos | _slot | _subtype | _abs_row
1 | 1 | CONTRACT REVENUE | [5 empty] | 1
2 | 2 | DESCRIPTION | [5 empty] | 2
3 | 3 | Original Contract |  | 185000 |  |  |  | 3
4 | 3 | CO 1 — CO #1: Upgraded kitchen window package |  | 2500 |  |  |  | 4 | 1
5 | 3 | CO 2 — CO #2: Add bathroom plumbing rough |  | 2000 |  |  |  | 4 | 2
6 | 5 | REVISED CONTRACT VALUE |  | 189500 |  |  |  | 5
7 | 7 | [6 empty] | 6
8 | 1 | COST BREAKDOWN | [5 empty] | 7
9 | 2 | CATEGORY / LINE ITEM |  | BUDGET | ACTUAL | % COMPLETE | REMAINING | 8
10 | 4 | LABOR |  | 46700 | 36100 | 0.77302 | 10600 | 9 |  | 1 | 1 | 1 | 1
11 | 3 | Site supervisor (16 weeks) | 01-001 | 24000 | 19500 | 0.8125 | 4500 | 9 |  | 2 | 1 | 2 | 2 | 10
12 | 3 | Carpentry crew | 01-002 | 18500 | 14200 | 0.76757 | 4300 | 9 |  | 3 | 1 | 3 | 2 | 11
13 | 3 | Cleanup / general labor | 01-003 | 4200 | 2400 | 0.57143 | 1800 | 9 |  | 4 | 1 | 4 | 2 | 12
14 | 4 | MATERIALS |  | 38800 | 33900 | 0.87371 | 4900 | 9 |  | 5 | 2 | 1 | 1
15 | 3 | Lumber package | 02-001 | 14800 | 14800 | 1 | 0 | 9 |  | 6 | 2 | 2 | 2 | 14
16 | 3 | Roofing materials | 02-002 | 6200 | 6500 | 1.0484 | -300 | 9 |  | 7 | 2 | 3 | 2 | 15
17 | 3 | Windows and exterior doors | 02-003 | 8400 | 8400 | 1 | 0 | 9 |  | 8 | 2 | 4 | 2 | 16
18 | 3 | Drywall and interior finishes | 02-004 | 5600 | 4200 | 0.75 | 1400 | 9 |  | 9 | 2 | 5 | 2 | 17
19 | 3 | Trim and millwork | 02-005 | 3800 | 0 | 0 | 3800 | 9 |  | 10 | 2 | 6 | 2 | 18
20 | 4 | SUBCONTRACTORS |  | 43200 | 31500 | 0.72917 | 11700 | 9 |  | 11 | 3 | 1 | 1
21 | 3 | Foundation / concrete sub | 03-001 | 12500 | 12500 | 1 | 0 | 9 |  | 12 | 3 | 2 | 2 | 20
22 | 3 | Electrical sub | 03-002 | 9800 | 7000 | 0.71429 | 2800 | 9 |  | 13 | 3 | 3 | 2 | 21
23 | 3 | Plumbing sub | 03-003 | 7400 | 5500 | 0.74324 | 1900 | 9 |  | 14 | 3 | 4 | 2 | 22
24 | 3 | HVAC sub | 03-004 | 8900 | 6500 | 0.73034 | 2400 | 9 |  | 15 | 3 | 5 | 2 | 23
25 | 3 | Painting sub | 03-005 | 4600 | 0 | 0 | 4600 | 9 |  | 16 | 3 | 6 | 2 | 24
26 | 4 | EQUIPMENT |  | 5800 | 4900 | 0.84483 | 900 | 9 |  | 17 | 4 | 1 | 1
27 | 3 | Excavator rental | 04-001 | 2800 | 2800 | 1 | 0 | 9 |  | 18 | 4 | 2 | 2 | 26
28 | 3 | Scaffolding rental | 04-002 | 1200 | 900 | 0.75 | 300 | 9 |  | 19 | 4 | 3 | 2 | 27
29 | 3 | Dumpster (3 hauls) | 04-003 | 1800 | 1200 | 0.66667 | 600 | 9 |  | 20 | 4 | 4 | 2 | 28
30 | 4 | OVERHEAD |  | 10750 | 8450 | 0.78605 | 2300 | 9 |  | 21 | 5 | 1 | 1
31 | 3 | Permits and inspection fees | 05-001 | 1850 | 1850 | 1 | 0 | 9 |  | 22 | 5 | 2 | 2 | 30
32 | 3 | Insurance allocation | 05-002 | 2400 | 1800 | 0.75 | 600 | 9 |  | 23 | 5 | 3 | 2 | 31
33 | 3 | Project management overhead | 05-003 | 6500 | 4800 | 0.73846 | 1700 | 9 |  | 24 | 5 | 4 | 2 | 32
34 | 6 | TOTAL PROJECT COST |  | 145250 | 114850 | 0.79071 | 30400 | 10
35 | 0 |  | Revised Cost Budget | 149750 |  |  |  | 0
36 | 0 | [6 empty] | 0
37 | 0 | [6 empty] | 0
38 | 0 | [6 empty] | 0
39 | 0 | [6 empty] | 0
40 | 0 | [6 empty] | 0
41 | 0 | [6 empty] | 0
42 | 0 | [6 empty] | 0
43 | 0 | [6 empty] | 0
44 | 0 | [6 empty] | 0
45 | 0 | [6 empty] | 0
46 | 0 | [6 empty] | 0
47 | 0 | [6 empty] | 0
48 | 0 | [6 empty] | 0
49 | 0 | [6 empty] | 0
50 | 0 | [6 empty] | 0
51 | 0 | [6 empty] | 0
52 | 0 | [6 empty] | 0
53 | 0 | [6 empty] | 0
54 | 0 | [6 empty] | 0
55 | 0 | [6 empty] | 0
56 | 0 | [6 empty] | 0
57 | 0 | [6 empty] | 0
58 | 0 | [6 empty] | 0
59 | 0 | [6 empty] | 0
60 | 0 | [6 empty] | 0
61 | 0 | [6 empty] | 0
62 | 0 | [6 empty] | 0
63 | 0 | [6 empty] | 0
64 | 0 | [6 empty] | 0
65 | 0 | [6 empty] | 0
66 | 0 | [6 empty] | 0
67 | 0 | [6 empty] | 0
68 | 0 | [6 empty] | 0
69 | 0 | [6 empty] | 0
70 | 0 | [6 empty] | 0
71 | 0 | [6 empty] | 0
72 | 0 | [6 empty] | 0
73 | 0 | [6 empty] | 0
74 | 0 | [6 empty] | 0
75 | 0 | [6 empty] | 0
76 | 0 | [6 empty] | 0
77 | 0 | [6 empty] | 0
78 | 0 | [6 empty] | 0
79 | 0 | [6 empty] | 0
80 | 0 | [6 empty] | 0
81 | 0 | [6 empty] | 0
82 | 0 | [6 empty] | 0
83 | 0 | [6 empty] | 0
84 | 0 | [6 empty] | 0
85 | 0 | [6 empty] | 0
86 | 0 | [6 empty] | 0
87 | 0 | [6 empty] | 0
88 | 0 | [6 empty] | 0
89 | 0 | [6 empty] | 0
90 | 0 | [6 empty] | 0
91 | 0 | [6 empty] | 0
92 | 0 | [6 empty] | 0
93 | 0 | [6 empty] | 0
94 | 0 | [6 empty] | 0
95 | 0 | [6 empty] | 0
96 | 0 | [6 empty] | 0
97 | 0 | [6 empty] | 0
98 | 0 | [6 empty] | 0
99 | 0 | [6 empty] | 0
100 | 0 | [6 empty] | 0
101 | 0 | [6 empty] | 0
102 | 0 | [6 empty] | 0
103 | 0 | [6 empty] | 0
104 | 0 | [6 empty] | 0
105 | 0 | [6 empty] | 0
106 | 0 | [6 empty] | 0
107 | 0 | [6 empty] | 0
108 | 0 | [6 empty] | 0
109 | 0 | [6 empty] | 0
110 | 0 | [6 empty] | 0
111 | 0 | [6 empty] | 0
112 | 0 | [6 empty] | 0
113 | 0 | [6 empty] | 0
114 | 0 | [6 empty] | 0
115 | 0 | [6 empty] | 0
116 | 0 | [6 empty] | 0
117 | 0 | [6 empty] | 0
118 | 0 | [6 empty] | 0
119 | 0 | [6 empty] | 0
120 | 0 | [6 empty] | 0
121 | 0 | [6 empty] | 0
122 | 0 | [6 empty] | 0
123 | 0 | [6 empty] | 0
124 | 0 | [6 empty] | 0
125 | 0 | [6 empty] | 0
126 | 0 | [6 empty] | 0
127 | 0 | [6 empty] | 0
128 | 0 | [6 empty] | 0
129 | 0 | [6 empty] | 0
130 | 0 | [6 empty] | 0
131 | 0 | [6 empty] | 0
132 | 0 | [6 empty] | 0
133 | 0 | [6 empty] | 0
134 | 0 | [6 empty] | 0
135 | 0 | [6 empty] | 0
136 | 0 | [6 empty] | 0
137 | 0 | [6 empty] | 0
138 | 0 | [6 empty] | 0
139 | 0 | [6 empty] | 0
140 | 0 | [6 empty] | 0
141 | 0 | [6 empty] | 0
142 | 0 | [6 empty] | 0
143 | 0 | [6 empty] | 0
144 | 0 | [6 empty] | 0
145 | 0 | [6 empty] | 0
146 | 0 | [6 empty] | 0
147 | 0 | [6 empty] | 0
148 | 0 | [6 empty] | 0
149 | 0 | [6 empty] | 0
150 | 0 | [6 empty] | 0
151 | 0 | [6 empty] | 0
152 | 0 | [6 empty] | 0
153 | 0 | [6 empty] | 0
154 | 0 | [6 empty] | 0
155 | 0 | [6 empty] | 0
156 | 0 | [6 empty] | 0
157 | 0 | [6 empty] | 0
158 | 0 | [6 empty] | 0
159 | 0 | [6 empty] | 0
160 | 0 | [6 empty] | 0
161 | 0 | [6 empty] | 0
162 | 0 | [6 empty] | 0
163 | 0 | [6 empty] | 0
164 | 0 | [6 empty] | 0
165 | 0 | [6 empty] | 0
166 | 0 | [6 empty] | 0
167 | 0 | [6 empty] | 0
168 | 0 | [6 empty] | 0
169 | 0 | [6 empty] | 0
170 | 0 | [6 empty] | 0
171 | 0 | [6 empty] | 0
172 | 0 | [6 empty] | 0
173 | 0 | [6 empty] | 0
174 | 0 | [6 empty] | 0
175 | 0 | [6 empty] | 0
176 | 0 | [6 empty] | 0
177 | 0 | [6 empty] | 0
178 | 0 | [6 empty] | 0
179 | 0 | [6 empty] | 0
180 | 0 | [6 empty] | 0
181 | 0 | [6 empty] | 0
182 | 0 | [6 empty] | 0
183 | 0 | [6 empty] | 0
184 | 0 | [6 empty] | 0
185 | 0 | [6 empty] | 0
186 | 0 | [6 empty] | 0
187 | 0 | [6 empty] | 0
188 | 0 | [6 empty] | 0
189 | 0 | [6 empty] | 0
190 | 0 | [6 empty] | 0
191 | 0 | [6 empty] | 0
192 | 0 | [6 empty] | 0
193 | 0 | [6 empty] | 0
194 | 0 | [6 empty] | 0
195 | 0 | [6 empty] | 0
196 | 0 | [6 empty] | 0
197 | 0 | [6 empty] | 0
198 | 0 | [6 empty] | 0
199 | 0 | [6 empty] | 0
200 | 0 | [6 empty] | 0
201 | 0 | [6 empty] | 0
202 | 0 | [6 empty] | 0
203 | 0 | [6 empty] | 0
204 | 0 | [6 empty] | 0
205 | 0 | [6 empty] | 0
206 | 0 | [6 empty] | 0
207 | 0 | [6 empty] | 0
208 | 0 | [6 empty] | 0
209 | 0 | [6 empty] | 0
210 | 0 | [6 empty] | 0
211 | 0 | [6 empty] | 0
212 | 0 | [6 empty] | 0
213 | 0 | [6 empty] | 0
214 | 0 | [6 empty] | 0
215 | 0 | [6 empty] | 0
216 | 0 | [6 empty] | 0
217 | 0 | [6 empty] | 0
218 | 0 | [6 empty] | 0
219 | 0 | [6 empty] | 0
220 | 0 | [6 empty] | 0
221 | 0 | [6 empty] | 0
222 | 0 | [6 empty] | 0
223 | 0 | [6 empty] | 0
224 | 0 | [6 empty] | 0
225 | 0 | [6 empty] | 0
226 | 0 | [6 empty] | 0
227 | 0 | [6 empty] | 0
228 | 0 | [6 empty] | 0
229 | 0 | [6 empty] | 0
230 | 0 | [6 empty] | 0
231 | 0 | [6 empty] | 0
232 | 0 | [6 empty] | 0
233 | 0 | [6 empty] | 0
234 | 0 | [6 empty] | 0
235 | 0 | [6 empty] | 0
236 | 0 | [6 empty] | 0
237 | 0 | [6 empty] | 0
238 | 0 | [6 empty] | 0
239 | 0 | [6 empty] | 0
240 | 0 | [6 empty] | 0
241 | 0 | [6 empty] | 0
242 | 0 | [6 empty] | 0
243 | 0 | [6 empty] | 0
244 | 0 | [6 empty] | 0
245 | 0 | [6 empty] | 0
246 | 0 | [6 empty] | 0
247 | 0 | [6 empty] | 0
248 | 0 | [6 empty] | 0
249 | 0 | [6 empty] | 0
250 | 0 | [6 empty] | 0
251 | 0 | [6 empty] | 0
252 | 0 | [6 empty] | 0
253 | 0 | [6 empty] | 0
254 | 0 | [6 empty] | 0
255 | 0 | [6 empty] | 0
256 | 0 | [6 empty] | 0
257 | 0 | [6 empty] | 0
258 | 0 | [6 empty] | 0
259 | 0 | [6 empty] | 0
260 | 0 | [6 empty] | 0
261 | 0 | [6 empty] | 0
262 | 0 | [6 empty] | 0
263 | 0 | [6 empty] | 0
264 | 0 | [6 empty] | 0
265 | 0 | [6 empty] | 0
266 | 0 | [6 empty] | 0
267 | 0 | [6 empty] | 0
268 | 0 | [6 empty] | 0
269 | 0 | [6 empty] | 0
270 | 0 | [6 empty] | 0
271 | 0 | [6 empty] | 0
272 | 0 | [6 empty] | 0
273 | 0 | [6 empty] | 0
274 | 0 | [6 empty] | 0
275 | 0 | [6 empty] | 0
276 | 0 | [6 empty] | 0
277 | 0 | [6 empty] | 0
278 | 0 | [6 empty] | 0
279 | 0 | [6 empty] | 0
280 | 0 | [6 empty] | 0
281 | 0 | [6 empty] | 0
282 | 0 | [6 empty] | 0
283 | 0 | [6 empty] | 0
284 | 0 | [6 empty] | 0
285 | 0 | [6 empty] | 0
286 | 0 | [6 empty] | 0
287 | 0 | [6 empty] | 0
288 | 0 | [6 empty] | 0
289 | 0 | [6 empty] | 0
290 | 0 | [6 empty] | 0
291 | 0 | [6 empty] | 0
292 | 0 | [6 empty] | 0
293 | 0 | [6 empty] | 0
294 | 0 | [6 empty] | 0
295 | 0 | [6 empty] | 0
296 | 0 | [6 empty] | 0
297 | 0 | [6 empty] | 0
298 | 0 | [6 empty] | 0
299 | 0 | [6 empty] | 0
300 | 0 | [6 empty] | 0
301 | 0 | [6 empty] | 0
302 | 0 | [6 empty] | 0
303 | 0 | [6 empty] | 0
304 | 0 | [6 empty] | 0
305 | 0 | [6 empty] | 0
306 | 0 | [6 empty] | 0
307 | 0 | [6 empty] | 0
308 | 0 | [6 empty] | 0
309 | 0 | [6 empty] | 0
310 | 0 | [6 empty] | 0
311 | 0 | [6 empty] | 0
312 | 0 | [6 empty] | 0
313 | 0 | [6 empty] | 0
314 | 0 | [6 empty] | 0
315 | 0 | [6 empty] | 0
316 | 0 | [6 empty] | 0
317 | 0 | [6 empty] | 0
318 | 0 | [6 empty] | 0
319 | 0 | [6 empty] | 0
320 | 0 | [6 empty] | 0
321 | 0 | [6 empty] | 0
322 | 0 | [6 empty] | 0
323 | 0 | [6 empty] | 0
324 | 0 | [6 empty] | 0
325 | 0 | [6 empty] | 0
326 | 0 | [6 empty] | 0
327 | 0 | [6 empty] | 0
328 | 0 | [6 empty] | 0
329 | 0 | [6 empty] | 0
330 | 0 | [6 empty] | 0
331 | 0 | [6 empty] | 0
332 | 0 | [6 empty] | 0
333 | 0 | [6 empty] | 0
334 | 0 | [6 empty] | 0
335 | 0 | [6 empty] | 0
336 | 0 | [6 empty] | 0
337 | 0 | [6 empty] | 0
338 | 0 | [6 empty] | 0
339 | 0 | [6 empty] | 0
340 | 0 | [6 empty] | 0
341 | 0 | [6 empty] | 0
342 | 0 | [6 empty] | 0
343 | 0 | [6 empty] | 0
344 | 0 | [6 empty] | 0
345 | 0 | [6 empty] | 0
346 | 0 | [6 empty] | 0
347 | 0 | [6 empty] | 0
348 | 0 | [6 empty] | 0
349 | 0 | [6 empty] | 0
350 | 0 | [6 empty] | 0
351 | 0 | [6 empty] | 0
352 | 0 | [6 empty] | 0
353 | 0 | [6 empty] | 0
354 | 0 | [6 empty] | 0
355 | 0 | [6 empty] | 0
356 | 0 | [6 empty] | 0
357 | 0 | [6 empty] | 0
358 | 0 | [6 empty] | 0
359 | 0 | [6 empty] | 0
360 | 0 | [6 empty] | 0
361 | 0 | [6 empty] | 0
362 | 0 | [6 empty] | 0
363 | 0 | [6 empty] | 0
364 | 0 | [6 empty] | 0
365 | 0 | [6 empty] | 0
366 | 0 | [6 empty] | 0
367 | 0 | [6 empty] | 0
368 | 0 | [6 empty] | 0
369 | 0 | [6 empty] | 0
370 | 0 | [6 empty] | 0
371 | 0 | [6 empty] | 0
372 | 0 | [6 empty] | 0
373 | 0 | [6 empty] | 0
374 | 0 | [6 empty] | 0
375 | 0 | [6 empty] | 0
376 | 0 | [6 empty] | 0
377 | 0 | [6 empty] | 0
378 | 0 | [6 empty] | 0
379 | 0 | [6 empty] | 0
380 | 0 | [6 empty] | 0
381 | 0 | [6 empty] | 0
382 | 0 | [6 empty] | 0
383 | 0 | [6 empty] | 0
384 | 0 | [6 empty] | 0
385 | 0 | [6 empty] | 0
386 | 0 | [6 empty] | 0
387 | 0 | [6 empty] | 0
388 | 0 | [6 empty] | 0
389 | 0 | [6 empty] | 0
390 | 0 | [6 empty] | 0
391 | 0 | [6 empty] | 0
392 | 0 | [6 empty] | 0
393 | 0 | [6 empty] | 0
394 | 0 | [6 empty] | 0
395 | 0 | [6 empty] | 0
396 | 0 | [6 empty] | 0
397 | 0 | [6 empty] | 0
398 | 0 | [6 empty] | 0
399 | 0 | [6 empty] | 0
400 | 0 | [6 empty] | 0
Note on H3: Stephen Sim: Hardcoded scale used by the budget consumed progress bar on 'Budget vs Actual'!E19. Controls total character width of the bar.
Note on H5: Stephen Sim: Stable anchor for Revised Cost Budget. Mirrors the formula at E89 (which sums Budget!F:F excluding category headers ending in -000), but at a fixed cell address so dashboard cells can reference it without drifting when rows are added/removed.
Note on H7: Stephen Sim: Stable anchor for Original Cost Budget — sums Budget!F:F excluding category headers (-000 codes) AND excluding change-order line items (where column G is non-blank). Fixed cell address so dashboard cells can reference it without drifting.