## About
CSSF eDesk cutover in 2027: prepare the official filing record
Alexander Akkarie ¦ Asset Velocity
Sheets
Read first
Cutover review
R3 reconciliation
R3 correction chain
Handover rehearsal
Sources
CSSF transition notice, 10 September 2026 — https://www.cssf.lu/en/2026/09/evolution-of-prudential-reporting-for-payment-institutions-electronic-money-institutions-and-crypto-asset-service-providers/

## Read first
Item | Instruction
Status | News & Analysis checked 26 October 2026. Recheck final instructions before live use.
Scope | Covered PI, EMI and Article 63 MiCAR CASP prudential returns only.
Route rule | Due through 31 March 2027: current route. Due from 1 April: new route, regardless of period.
Test window | 1 January to 31 March 2027; non-official.
Submission | Manual eDesk or S3 JSON. Optional data-feed API is separate from submission.
Assumptions | All deadlines, IDs, amounts and outcomes in this workbook are invented.
Use | Copy the record design; replace facts with verified local data and actual authority instructions.
Static values | No formulas, macros or live links to reporting data. Arithmetic checked manually.
Retention | Preserve approved data, exact payloads, approvals, receipt meanings and correction lineage.
Readiness dependency | Owner must confirm final circular, schemas, access, status meanings and correction mechanics.
This workbook does not generate a regulatory filing or determine compliance.

## Cutover review
Return / due date | Test evidence | Official evidence | Decision at 8 April
R1 February / 20 March | TEST-01, 19 March | CUR-01, 18 March; approved V1 matched | Complete using CUR-01 and data check
R2 March / 20 April | TEST-02, 20 March; synthetic data | None; real March V1 now approved | Official filing open; internal target 14 April
R3 Q1 / 25 April | Not relevant to official filing status | NEW-03, 6 April; sent V2; approved V3 | Submitted; reconciliation exception open
Due dates and evidence references are hypothetical, not CSSF requirements. Actual acknowledgement meanings must be checked.

## R3 reconciliation
Measure / item | Submitted V2 EUR | Approved V3 EUR | Difference EUR
Same ten source balances | 240000 | 250000 | 10000
Explained change B07 | Retained source comparison | Approved source correction | 6000
Explained change B09 | Retained source comparison | Approved source correction | 4000
Other eight balances | Unchanged | Unchanged | 0
Internal sum of ten source balances only. Not a CSSF reporting line or a sum across unrelated cells. 250000 - 240000 = 10000; 6000 + 4000 = 10000. Individual balances also reconciled; totals alone can conceal offsetting errors.

## R3 correction chain
Record | Meaning | Completed example state
A3 / V3 | Approved source data | Retained separately from original sent payload
V2 / NEW-03 | Original payload and official evidence | Immutable historical record
REC-03 | Balance-level comparison | B07 +6000; B09 +4000; eight balances unchanged
COR-A1 | 9 April correction approval | Authorised lead checked actual procedure
COR-03 | Corrective submission | Uses approved V3; linked to R3 and NEW-03
NEW-03-C | Official correction evidence | Assumed procedure confirms required filing status
REC-03-C | Received-content verification | Intended corrective payload matches V3; sum EUR250000
Final decision | Corrective filing evidenced; internal check closed | Retain original discrepancy history
The correction sequence is an operating example. No portal edit, replacement flag or regulatory acknowledgement semantics are prescribed. Receipt-only or unidentified content leaves verification open.

## Handover rehearsal
Check | Owner in example | Exit evidence
Final requirements | Reporting policy owner | Applicable circular, schema and deadlines confirmed
Access and chosen route | Submission operations owner | Authorised operator can use actual route
Approved versus sent | Reporting lead | Payload comparison and approval retained
Receipt meaning | Reporting lead | Actual required official status established
Deliberate version mismatch | Second reviewer | Difference detected; source and submitted versions preserved
Correction procedure | Authorised reporting lead | Real procedure confirmed before action
Handover | Second reviewer | Can reconstruct complete filing chain without operator memory
Assign real names and actual local evidence before operational use. These are readiness tasks, not completed work at a real firm.