## Schedule of Values
|  | To Client: | From Contractor: | [5 empty] | Application No.: | 1
|  | John Doe | Jane Smith & Co. | [5 empty] | Application Date: | 2023-01-01
|  | 123 Anywhere ST. | 123 Anywhere ST. | [5 empty] | Project Name: | JOHN DOE HOME
|  | City, ST 12345 | City, ST 12345 | [5 empty] | Original Contract Date: | 2023-01-01
The Contractor certifies that, to the best of their knowledge and belief, the work described in this application has been completed in accordance with the project agreement. All previous payments received have been properly applied to prior work, and the amount requested represents the current value of work completed to date.
CONTRACTOR'S APPLICATION FOR PAYMENT
APPLICATION IS MADE FOR PAYMENT, AS SHOWN BELOW, IN CONNECTION WITH THE CONTRACT. CONTINUATION SHEET IS ATTACHED.
CONTRACTOR
| 1 | ORIGINAL CONTRACT SUM |  | 1399000 |  | By: |  |  | Date:
| 2 | NET CHANGE BY CHANGE ORDERS |  | 37380
| 3 | CONTRACT SUM TO DATE |  | 1436380 |  | State of:
(Line 1 ± 2)
| 4 | TOTAL COMPLETED & STORED TO DATE |  | 713105 |  | County of:
(Total on Column H of Continuation Sheet)
| 5 | RETAINAGE |  |  |  | Signature:
| a. | % of Completed Work | 5% | 35655.25
| b. | % of Stored Work | 5% | 0 |  | NOTARY | Subscribed and sworn to before me this
|  | TOTAL RETAINAGE |  | 35655.25 |  |  |  |  | day of
(Line 5a + 5b, or Total in Column L of Continuation Sheet)
| 6 | TOTAL EARNED LESS RETAINAGE |  | 677449.75 |  | Notary Public:
|  | (Line 4 Less Line 5 Total) |  |  |  | My Commission expires:
| 7 | LESS: PREVIOUS CERTIFICATES FOR PAYMENT |  | 0
(Line 6 From Prior Certificate)
| 8 | CURRENT PAYMENT DUE |  | 677449.75 |  | ARCHITECT'S CERTIFICATE FOR PAYMENT
| 9 | BALANCE TO FINISH, INCLUDING RETAINAGE |  | 758930.25 |  | Based on available observations and supporting information, the Owner or Project Representative confirms that the work has progressed as indicated, meets the required standards of quality, and that the Contractor is eligible for payment in the amount shown.
(Line 3 Less Line 6)
|  | CHANGE ORDER SUMMARY | ADDITIONS | DEDUCTIONS
|  | Total changes approved in previous months |  |  |  | Amount Certified: | 677449.75
|  | Total approved this Month | 37380
|  | TOTALS | 37380 | 0 |  | ARCHITECT
|  | NET CHANGES by Change Order | 37380 |  |  | Signature:
Continuation Sheet
| Type | Description | Scheduled Value | From Previous Applications | This Period | Materials Presently Stored | Total Completed & Stored to Date | % Completed |  | Balance To Finish | Retainage
1 | ◯ | Site Preparation
1 | ◆ | Land Clearing | 31500 | 15750 | 15750 |  | 31500 | 100% | 100% | 0 | 1575
1 | ◆ | Excavation | 63000 | 44100 | 18900 |  | 63000 | 100% | 100% | 0 | 3150
1 | ◆ | Grading | 105000 | 52000 | 53000 |  | 105000 | 100% | 100% | 0 | 5250
1 | ◯ | Foundations
1 | ◆ | Foundation Concrete | 105000 | 42000 | 63000 |  | 105000 | 100% | 100% | 0 | 5250
1 | ◆ | Rebar and Reinforcement | 105000 | 42000 | 63000 |  | 105000 | 100% | 100% | 0 | 5250
1 | ◆ | Structural Framing | 310000 | 0 |  |  | 0 | 0% | 0% | 310000 | 0
1 | ◆ | Steel Beams and Columns | 210000 | 0 | 100000 |  | 100000 | 47.62% | 47.62% | 110000 | 5000
1 | ◆ | Installation Labor | 100000 | 52500 | 25000 |  | 77500 | 77.5% | 77.5% | 22500 | 3875
1 | ◯ | Roofing
1 | ◆ | Roof Trusses | 105000 | 42000 |  |  | 42000 | 40% | 40% | 63000 | 2100
1 | ◆ | Roofing Materials | 52500 | 21000 |  |  | 21000 | 40% | 40% | 31500 | 1050
1 | ◯ | Electrical
1 | ◆ | Main Wiring | 52500 | 4725 |  |  | 4725 | 9% | 9% | 47775 | 236.25
1 | ◆ | Lighting Fixtures | 31500 | 6300 |  |  | 6300 | 20% | 20% | 25200 | 315
1 | ◆ | Electrical Panels | 42000 | 0 |  |  | 0 | 0% | 0% | 42000 | 0
1 | ◯ | Plumbing
1 | ◆ | Piping | 40000 | 14700 |  |  | 14700 | 36.75% | 36.75% | 25300 | 735
1 | ◆ | Fixtures Installation | 46000 | 0 |  |  | 0 | 0% | 0% | 46000 | 0
1
1
1
1
1 | ◯ | CHANGE ORDER
1 | CO | Geotech Fabric & Stone | 24000 | 0 | 24000 |  | 24000 | 100% | 100% | 0 | 1200
1 | CO | Sewer Changes and Water Taps | 1800 | 0 | 1800 |  | 1800 | 100% | 100% | 0 | 90
1 | CO | Additional Stone | 580 | 0 | 580 |  | 580 | 100% | 100% | 0 | 29
1 | CO | 3rd Party Inspection Fees | 1000 | 0 | 1000 |  | 1000 | 100% | 100% | 0 | 50
1 | CO | Extra Grading Work | 10000 | 0 | 10000 |  | 10000 | 100% | 100% | 0 | 500
1 |  | Total | 1436380 | 337075 | 376030 | 0 | 713105 |  | 49.65% | 723275 | 35655.25

## DISCLAIMER
LEGAL DISCLAIMER
1. No Warranty or Liability
This spreadsheet template is provided “as is,” without any warranties, express or implied. While every effort has been made to ensure accuracy, the creator makes no guarantees regarding completeness, reliability, or suitability for any specific purpose.
By using this template, you acknowledge that:
You are solely responsible for verifying all calculations, data accuracy, and compliance with applicable laws and regulations.
The creator is not liable for any errors, omissions, financial losses, business decisions, or other consequences resulting from the use of this template.
2. No Financial, Legal, or Professional Advice
This template is for informational purposes only and should not be considered financial, legal, tax, or professional advice. Consult a qualified professional before making any financial, business, or tax-related decisions.
3. Software Compatibility
This template is designed for use with Microsoft Excel. Some features, formulas, or formatting may not function properly in other spreadsheet applications or versions. If you experience compatibility issues, please refer to the template’s documentation or use the recommended software.
4. Data Privacy
The creator does not collect, store, or have access to any data entered into this spreadsheet. Users are responsible for ensuring their own data privacy and security.
5. Usage & Distribution Restrictions
This template is licensed for personal or business use only by the original purchaser.
Redistribution, resale, or modification for resale without prior written consent is strictly prohibited.
Unauthorized sharing of this template or its contents violates copyright laws and may result in legal action.
6. No Ongoing Support or Customization
This template is sold as a standalone product. While it includes basic instructions, ongoing technical support, troubleshooting, or customization requests are not included. If you need modifications, you are responsible for making those changes independently.
Need Assistance?
For questions, licensing inquiries, or permissions, contact: mightytemplate@gmail.com
© Copyright 2025 Mighty Template