## Dashboard & Instructions
Volve RFP Tender Overview Checklist
Empowering contractors with AI-driven insights
Built to work across construction projects. Use this template to summarise an RFP or tender pack into a bid-ready overview. Capture facts, obligations, dependencies, and risks. If something is not provided, mark it clearly as Not provided.
1 | Navigate to the Checklist | Click the "Start Checklist" button to begin your bid-ready assessment.
2 | Review Each Category | Work through the 7 categories: Project Scope, Site & Ground Conditions, Schedule & Sequencing, Permits & Stakeholders, HSE & Sustainability, Commercial, and Contract & Risk Terms.
3 | Assess Each Item | For each checklist item, review the description and expand to see detailed guidance.
4 | Set Status & Risk Level | Select the review status (Not Started, In Review, Pending, Completed) and risk level (Low, Medium, High) using the dropdown options.
5 | Document Your Findings | Add notes, action items, and clarifications specific to your project in the notes section.
6 | Leverage AI Insights | Use the detailed guidance in each item to understand construction-specific risks and best practices.
Automate your bid readiness assessment and mitigate risks with Volve AI!
Disclaimer
This checklist is general information to help spot commercial contract risks, project scope gaps, and bid readiness issues. It is not legal advice and isn't tailored to any project, contract form, or jurisdiction. You should get qualified legal, commercial, and technical advice before acting on it. Use this checklist as a starting point for your bid assessment, not as a substitute for professional guidance.
How to Use This Tool
Visit volvetech.com to learn more and book a demo >

## Checklist
Topic | Subtopic | What to check | Owner | Status | Risk Level | Key findings / summary | RFP source reference | Clarifications needed
About | Client | - Issuing organisation name - Employer/Client representative and main point of contact - Delivery stakeholders named (PM, QS/Commercial, Designer, Operator)
| Project type | - Sector: buildings / infrastructure / industrial / energy / data centre / other - New build vs refurbishment/rehab - Any live-operations constraints (occupied building, operational railway/road, live plant)
| Size | - Key scale metric stated (area, number of floors, length, capacity) - If missing: record as “Not provided” and flag as risk to clarify
| Indicative budget / contract value | - Stated budget/estimate and currency - Inclusions/exclusions (tax, client-supplied items, contingency) - Any budget cap or affordability constraint
| Construction period | - Planned start and completion dates - Any mandated milestones (phased handovers, sectional completion) - Long-lead constraints implied by dates
| Project location | - City/region/country - Site context (dense urban, remote, coastal, sensitive environment)
| Contract format | - Form of contract named (or bespoke) - Delivery model (DBB, D&B, EPC, CM, framework/call-off) - Whether deviations are permitted and how they must be submitted
Procurement | Procurement method | - Open/restricted/negotiated/framework - Single-stage vs two-stage - If interviews/presentations are required
| Submission deadline | - Submission date/time and time zone - Validity/binding period - Required number of copies/portal rules - Rules for addenda and acknowledgement
| Clarification process | - Deadline for questions - Format and channel (portal/email) - Site visit requirements and timing - How responses are issued (addenda, Q&A log)
| Evaluation criteria | - Award method (MEAT/lowest price/quality weighted) - Weightings and pass/fail thresholds - Mandatory templates/forms and scoring rules - Any abnormally low bid rules
| Qualification requirements | - Mandatory accreditations/certifications - Financial thresholds, bonding capacity - Relevant project references and minimum experience - Key personnel requirements
Scope & execution | Project objectives | - Hard musts (time, cost, safety, sustainability, operational constraints) - Stated trade-offs (speed vs cost, quality vs time) - Objectives that are missing or vague (flag for clarification)
| Scope summary | - Major work elements included (enabling, civils/structure, envelope, MEP, finishes, external works) - Key deliverables and acceptance criteria - Major exclusions stated (and missing exclusions you would expect) - Client deliverables (permits, utilities, access, surveys, owner-furnished items, info release dates)
| Existing asset constraints (if relevant) | - Requirements to maintain operations during works - Possession/shutdown windows - Temporary works and protection requirements - Interfaces with occupants/operators
| Delivery approach and digital | - Collaboration model (early contractor involvement, workshops) - Digital requirements (BIM level, CDE platform, naming conventions, information deliverables) - Reporting cadence and dashboards/KPIs
| Key risks stated by client | - Up to five specific, residual risks the client explicitly highlights - Risk owners stated or implied - Any “boilerplate risk” that hides real issues (flag)
Site | Ground conditions overview | - Ground investigation availability and adequacy - Key geotechnical conditions and uncertainties - Contamination/hazardous materials indications - Underground utilities risk and mapping quality
| Site constraints | - Physical constraints (topography, access limits, restricted zones) - Environmental constraints (flooding, protected areas, noise/vibration limits) - Heritage/overlay restrictions where applicable
| Surveys and investigations | - Completed surveys provided (GI, utilities mapping, structural surveys, asbestos/hazmat, traffic) - Outstanding surveys and who owns them - Gaps that affect method, programme, or price
| Access and logistics | - Delivery routes, time windows, permits - Laydown, storage, crane/hoist feasibility - Working hours, local restrictions, event/season constraints - Client/authority prerequisites (road closures, escorts, approvals)
Schedule & sequencing | Timeline and phasing | - Key milestones, sectional handovers, mandated completion dates - Phasing requirements and interfaces between packages - Incentives/bonuses and delay consequences stated - Known schedule risks the client acknowledges
| External dependencies | - Utility companies and authority dependencies - Access/possession windows and shutdown constraints - Prerequisite design/info releases and hold points - Commissioning constraints and operational cutovers
Permits & stakeholders | Planning and permits | - Permit list required for start and for completion - Current status and remaining submissions - Responsible party for applications and approvals - Key dates, validity windows, and constraints
| External stakeholders and surroundings | - Authorities, utilities, operators, neighbours - Required engagement/consultation steps - Noise/vibration/dust/traffic constraints and monitoring - Commitments and dependencies that affect programme/cost
HSE & sustainability | Sustainability and environmental | - Required certifications/targets and definitions - Reporting/verification requirements and data inputs - Embodied carbon / waste / energy requirements if stated - Client deliverables needed to meet targets
| Health, safety and security | - Mandatory plans and controls (RAMS, permits to work, lifting, confined space, hot works) - Training/inductions requirements - Emergency arrangements and site medical - Security requirements and restricted access rules
Commercial | Payment terms overview | - Pricing model (lump sum, remeasurement, target cost, GMP, unit rates) - Indexation/inflation and currency/FX allocation - Payment cycle and certification basics - Retention/advance payments stated - Guarantees, bonds, and insurance requirements referenced in commercial docs
| Options and allowances | - Provisional sums/allowances and how they’re managed - Alternates and bid options allowed/required - Value engineering rules and approval route
| Innovation and added value | - Where innovation is invited and how it’s evaluated - Constraints (prohibited alternatives, minimum performance) - Required approvals and evidence for proposed alternatives
Contract and risk terms | Document hierarchy | - Order of precedence stated - Conflicts between ITT, contract, schedules, specs, drawings flagged - Amendments clearly identified and overriding base form
| Change control / variations | - How changes are instructed (written instruction rules) - Valuation basis (rates/dayworks/OH&P/prelims) - Time impact process linked to EOT - Interim valuation and dispute route
| EOT and delay cost | - EOT grounds and notice/time bars - Cost entitlement for client-caused delay/disruption - Admin burden and substantiation requirements
| Delay damages (LDs) | - Rate and total cap - Sectional completion triggers - Sole remedy vs additional damages exposure - Treatment of client-caused delay/dependencies
| Liability cap | - Cap amount and basis (aggregate/per claim) - Carve-outs that bypass cap - Indirect/consequential loss position where applicable
| Indemnities | - Indemnity triggers (fault/control vs broader) - Third-party and employer design exposure - Alignment with insurability
| Bonds/guarantees | - Type (on-demand vs conditional) - Amount, expiry/sunset, step-down - Call conditions and notice/cure
| Insurance | - Required policies and limits - Unusual endorsements/waivers/joint names - Deductibles and insurability concerns
| Payment mechanics | - Certification, pay-less/set-off process - Retention % and release triggers - Final account timetable
| Termination | - Termination for convenience/default - Settlement heads (work done, committed costs, demob, OH&P) - Step-in and materials ownership provisions
| Design responsibility (if any) | - Standard of care vs outcome/performance obligations - Reliance on employer information - Novation or design coordination obligations
| Disputes and governing terms | - Governing law / venue - Dispute mechanism and escalation steps - Notice/service requirements that create time-bar risk

## Volve Feature Guide
Unlock Advanced Contract Analysis with Volve AI
Manual Contract Review vs. Volve AI
Feature | Manual Review | Volve AI
Clause Identification | Time-consuming, prone to human error, requires legal expertise. | Instant, AI-powered identification of all critical clauses.
Risk Assessment | Subjective, inconsistent, relies on individual experience. | Objective, consistent risk flagging based on industry best practices.
Compliance Tracking | Manual checklists, difficult to audit, easily overlooked. | Automated tracking, audit trails, real-time compliance status.
Decision Support | Relies on memory and fragmented notes. | Contextual insights, mitigation strategies, and actionable recommendations.
Efficiency | Slow, costly, diverts resources from core activities. | Rapid, cost-effective, frees up legal and project teams.
Ready to transform your tender process?
Book a personalised demo of Volve AI today >