## Start Here
GLOSSA
The Outcome Mapping Template
Tie every requirement to a business outcome — so delivery never loses sight of what was sold.
How to use this template
1. Define your outcomes.
Open the Outcomes tab. Write down the business outcomes your client is buying — the reasons the deal closed. A good outcome has a baseline, a goal, and a financial impact.
2. Map outcomes to capabilities.
Open the Capabilities tab. For each outcome, list the capabilities (chunks of work, mechanisms, or solution patterns) that will deliver it. This is where you make the 'how' explicit.
3. Tie requirements to capabilities.
Open the Requirements tab. For each requirement in your project, link it to a capability. Anything that doesn't map is a candidate for a scope conversation.
4. Come back to it.
Revisit weekly. People forget outcomes and try to renegotiate scope all the time. The point of writing this down is to keep everyone anchored.
Why this works
• Your delivery team gets the language to push back on scope creep.
• Live clients stop churning because the project actually solves their business problem.
• You build a reusable library of outcomes-to-capabilities patterns you can scale across projects.
Want this done automatically? Glossa pulls outcomes from your sales conversations, generates structured requirements, and maps them to capabilities — without the spreadsheet. → glossapro.ai/outcomes

## 1. Outcomes
Define your outcomes
List the business outcomes your client is buying. A good outcome has a baseline (where they are today), a goal (where they want to be), and a financial impact (why it matters). Once you've added requirements on the Requirements tab, come back here and check the Requirements Count column — how are you planning to delivery any outcome with zero requirements?
OUTCOMES
Outcome ID | Outcome Name | Description | Baseline (today) | Goal | Financial Impact | Mechanism (optional) | Requirements Count
O-001 | Reduce manual claims processing headcount | Replace the manual claims review team with automated workflows in the new platform. | 12 FTEs reviewing claims manually, ~40 hrs/week each | Reduce to 3 FTEs handling exceptions only | $1.2M annual savings | Auto-routing + rules engine + exception queue | 1
↑ Example row — delete this when you're ready to use the template.

## 2. Capabilities
Map outcomes to capabilities
Capabilities are the chunks of work — the mechanisms, solution patterns, or features — that deliver an outcome. Multiple capabilities can serve one outcome, and one capability can serve multiple outcomes.
CAPABILITIES
Capability ID | Capability Name | Description | Linked Outcome ID | Category | Reusable? | Notes
C-001 | Automated claims routing | Inbound claims auto-routed to the correct queue based on claim type, state, and risk profile. | O-001 | Workflow automation | Yes | Reused on prior carrier projects — strong pattern.
↑ Example row — delete this when you're ready to use the template.

## 3. Requirements
Tie requirements to capabilities
Paste your project requirements into this tab. For each requirement, link it to a capability. Any requirement that doesn't map to a capability is a scope conversation waiting to happen — flag it and ask 'why are we doing this?'
REQUIREMENTS
Req ID | Requirement | Source | Linked Capability ID | Linked Outcome (auto) | Priority | Status | Notes
R-001 | System shall auto-route incoming claims to the correct queue based on claim type and state. | Discovery call 3/12 | C-001 | Reduce manual claims processing headcount | High | In Progress | Confirmed in 3/12 call with Ops lead.
↑ Example row — delete this (but keep the formula in column F) when you're ready to use the template.