## Work Schedule
Works Schedule No:
Custodian:
Asset:
Item:
Objective:
Date:
Final Scope of Works:
Task(s) / Product | Indicate Estimate or Firm | Volunteer Labour / Paid Labour / Materials / Service | Notes | Qty | Unit Price (exc GST) | Total Cost | Funding Source |  |  |  |  | TfNSW Stream 2 Funding Contribution | Total custodian funding contribution
[7 empty] | Committed wages (costs of personnel already on staff) | Extra wages (costs of casuals brought in for project) | Volunteer and stock in hand | Grants, sponsorships and donations | Goods and services
Stage 1 planning the work | [5 empty] | 0 | [5 empty] | 0 | 0
Write proposal, scope of work, heritage impact statement, cost the work, evaluation quotations, submit paperwork to THNSW. | [5 empty] | 0 | [5 empty] | 0 | 0
[6 empty] | 0 | [5 empty] | 0 | 0
[6 empty] | 0 | [5 empty] | 0 | 0
[6 empty] | 0 | [5 empty] | 0 | 0
Stage 2 doing the work | [5 empty] | 0 | [5 empty] | 0 | 0
[6 empty] | 0 | [5 empty] | 0 | 0
[6 empty] | 0 | [5 empty] | 0 | 0
[6 empty] | 0 | [5 empty] | 0 | 0
[6 empty] | 0 | [5 empty] | 0 | 0
[6 empty] | 0 | [5 empty] | 0 | 0
[6 empty] | 0 | [5 empty] | 0 | 0
[6 empty] | 0 | [5 empty] | 0 | 0
Stage 3 processing the paperwork | [5 empty] | 0 | [5 empty] | 0 | 0
Collating receipts against expenditure sheet, writing completion report, submitting to THNSW. | [5 empty] | 0 | [5 empty] | 0 | 0
[7 empty] | Wages | Extra wages | In kind | Donations | G & S
Subtotal | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GST | [6 empty] | Not applied | Not applied | Not applied | 0 | 0 | 0 | 0
Wages oncosts 30%, o/heads 15% | [6 empty] | 0 | 0 | 0 | Not applied | Not applied | 0 | 0
Total | [5 empty] | 0 | [5 empty] | 0 | 0
Other Comments:
|  |  |  | Custodian approved funding amoun (inc GST) is: | [7 empty] | 0
Prepared by: |  |  |  | TfNSW approved funding amount (inc GST) is: | [7 empty] | 0
[9 empty] | ___________________ |  |  | __/__/____
|  |  |  | Approved by |  |  |  |  | Signature |  |  | Date
________________________
Signature | Date

## WS Example
Works Schedule No: | Custodian / Year / work schedule number (eg THNSW/16/03 or BSC/16/01)
Custodian: | Name of custodian listed on custody management agreement (eg Berrigan Shire Council)
Asset: | Name of the object as listed on the custody management agreement (eg Wagga Wagga Porter's Room)
Objective: | Briefly what you are trying to achieve - as per proposal
Date:
Final Scope of Works: | Precisely what work you are proposing to carry out as listed step-by step below
Task(s) / Product | Indicate Estimate or Firm | Volunteer Labour / Paid Labour / Materials / Service | Notes | Qty | Unit Price (exc GST) | Total Cost | Type of cost |  |  |  |  | TfNSW Stream 2 Funding Contribution | Total custodian funding contribution | THNSW Stream 1 Funding Contribution
[7 empty] | Committed wages (costs of personnel already on staff) | Extra wages (costs of casuals brought in for project) | Volunteer and stock in hand | In kind and dontations | Goods and services
Stage 1 planning the work | [11 empty] | 0 | 0
Write proposal, scope of work, heritage impact statement, cost the work, evaluation quotations, submit paperwork to THNSW. | E | Volunteer Labour | 1 volunteer for 40 hours | 40 | 35 | 1400 |  |  | 1400 |  |  | 0 | 1400
Stage 2 doing the work | [11 empty] | 0 | 0
Repair/replace window sills | E | Volunteer Labour | 4 volunteers for 20 hours each | 80 | 35 | 2800 |  |  | 2800 |  |  | 0 | 2800
| F | Materials | Timber | 1 | 400 | 400 |  |  |  |  | 400 | 400 | 0
| E | Materials | Wood screws, glue, sand paper, bog | 1 | 50 | 50 |  |  |  |  | 50 | 50 | 0
Replace gutters | F | Service | ABC Gutter Company | 1 | 600 | 600 |  |  |  |  | 600 | 600 | 0
Paint building | E | Volunteer Labour | 4 volunteers for 36 hours each | 144 | 35 | 5040 |  |  | 5040 |  |  | 0 | 5040
| E | Materials | Primer, rollers, paint brushes, thinners - donation from local hardware | 1 | 150 | 150 |  |  |  | 150 |  | 0 | 150
| E | Materials | Paint - from custodian's store | 1 | 300 | 300 |  |  | 300 |  |  | 0 | 300
Stage 3 processing the paperwork | [11 empty] | 0 | 0
Maintain expenditurerecords, write job completion report, submit to THNSW | E | Volunteer Labour | 1 volunteer for 10 hours | 10 | 35 | 350 |  |  | 350 |  |  | 0 | 350
[7 empty] | Wages | Extra wages | In kind | Donations | G & S
Subtotal | [5 empty] | 11090 | 0 | 0 | 9890 | 150 | 1050 | 1050 | 10040 | 0
GST | [6 empty] | Not applied | Not applied | Not applied | 15 | 105 | 15 | 105 | 0
Wages oncosts 30%, o/heads 15% | [6 empty] | 0 | 0 | 659.3333 | Not applied | Not applied | 0 | 659.3333
Total | [11 empty] | 1065 | 10804.3333 | 0
Other Comments:
|  |  |  | Custodian approved funding amount (inc GST) is: | [7 empty] | 10804.3333
Prepared by: |  |  |  | TfNSW approved funding amoungt (inc GST) is: | [7 empty] | 1065
[9 empty] | ___________________ |  |  | __/__/____
|  |  |  | Approved by |  |  |  |  | Signature |  |  | Date
________________________
Signature | Date

## Expenditure tracking
BUDGET AND EXPENDITURE TRACKING
Budget - as listed in the approved work schedule
CUSTODIAN: |  |  | 2016 | Wages (committed) | Wages (extra) | Volunteer contribution | Parts from stock | Donations and in-kind | Goods and services | TOTAL
|  |  | JUL–SEP | [6 empty] | 0
W/S NO: |  |  | OCT–DEC | [6 empty] | 0
|  |  | JAN–MAR | [6 empty] | 0
PROJECT |  |  | APR–JUN | [6 empty] | 0
|  |  | TOTALS | [6 empty] | 0
Date | Supplier | Description |  | Wages (committed) | Wages (extra) | Volunteer contribution | Parts from stock | Donations and in-kind | Goods and services | TOTAL
Totals spent |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Amts remaining |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
All receipts must be retained and copies provided with the expenditure spreadsheet.