## Timeline
FILEBIRD TEMPLATES
Data migration planner
Tab 1: Timeline. Enter your go-live date in the shaded cell below and every other date in the planner moves with it.
Filebird template. A starting point only: check it against your jurisdiction’s rules and your law society or state bar’s requirements.
Go-live date, a Monday (input) |  | Firm (input) | Signs off for the firm (input) | Migration lead (input) | Day 1 starts | Tasks done | Go-live check
2026-11-16 |  | [Firm name] | [Name, role] | [Name] | 2026-11-02 | 0 of 13 | Monday: good
Day | Stage | What happens | Done when | Owner | Due date | Status | Notes
Before | Kickoff and go-live date agreed | Kickoff call. Agree the go-live date, the people involved and who at the firm signs off each stage. Freeze changes to matter types and custom fields in the current system until go-live. | Go-live date and sign-off person entered at the top of this tab. | Practice manager | 2026-10-30 | Not started
Day 1 | Full export from current system | Request a full export: contacts, matters (open and closed), time, invoices, trust ledgers and documents. Check every file opens and note the row counts. | Export received, stored securely and row counts noted on the Data inventory tab. | Practice manager | 2026-11-02 | Not started | Ask your current provider early. Some take several days to produce a full export.
Day 2 | Data inventory confirmed | List every source of data on the Data inventory tab, including spreadsheets, shared drives and mailboxes outside the current system. Decide what moves, what is archived and what stays. | Inventory signed off on the Sign-off log. | Practice manager | 2026-11-03 | Not started
Day 3 | Matter types mapped to templates | Map each matter type in the current system to a practice-area matter template. Merge duplicates and retire types nobody uses. | Every open matter has a template to land in. | Principal and team leads | 2026-11-04 | Not started
Day 4 | Users, rates and fields mapped | Map users and permissions, billing rates (by person and by matter where they differ), custom fields and key-date types. | Mapping approved on the Sign-off log. | Practice manager | 2026-11-05 | Not started
Day 5 | Import to staging account | Import the Day 1 export into a staging account. Nobody works in staging: it exists to be checked. | Import complete, with every error in the import log explained. | Filebird migration specialist | 2026-11-06 | Not started
Day 6 | Trust balances checked by client | Compare every client ledger balance in staging with the current system at the cut-off date, on the Trust balance check tab. Check the total against the reconciled trust bank balance. | Every ledger agrees and the total matches the bank. Signed off by a principal. | Bookkeeper and principal | 2026-11-09 | Not started
Day 7 | Unbilled time and debtors agreed | Compare unbilled time and unpaid invoices, matter by matter, with the current system’s reports. Agree how part-billed matters carry across. | Totals agree by matter and by fee earner. | Bookkeeper | 2026-11-10 | Not started
Day 8 | Sample of 20 matters reviewed | Open 20 matters across practice areas and fee earners. Check parties, key dates, documents, time, invoices and trust history against the current system. | Every issue logged with an owner. Nothing open that blocks go-live. | Team leads | 2026-11-11 | Not started
Day 9 | Firm review and fixes | Team leads review their own matters in staging. Fix mapping issues and rerun the affected parts of the import. | Fix list cleared, or remaining items accepted by the firm. | Practice manager | 2026-11-12 | Not started
Day 10 | Final export, import and recheck | At close of business, take the final export and import it. Rerun the row counts and the trust balance check. Make the current system read-only. | Trust balances agree at the final cut-off and the firm approves go-live. | Filebird migration specialist | 2026-11-13 | Not started | Nothing new goes into the old system after the final export.
Monday | Team live in Filebird | Everyone works in Filebird from the start of the day, with the migration team on call. | First day’s time, receipts and trust entries recorded in Filebird. | Everyone | 2026-11-16 | Not started | Keep the old system read-only for reference. Do not cancel it yet.
Week 1 | First week review | Review open questions, check the first trust entries and agree when the old system can be archived. | Open questions closed or assigned. Archive date agreed. | Practice manager | 2026-11-20 | Not started

## Data inventory and mapping
FILEBIRD TEMPLATES
Data migration planner
Tab 2: Data inventory and mapping. List every source of data, including spreadsheets and shared drives outside your current system, then decide where each one goes.
Filebird template. A starting point only: check it against your jurisdiction’s rules and your law society or state bar’s requirements.
Sources listed |  | To migrate |  | To archive |  | To leave where it is |  | Rows done
17 |  | 14 |  | 1 |  | 2 |  | 0 of 17
Ref | Source (system or location) | Data | What it holds | Records (approx.) | Action | Destination in Filebird | Mapping notes | Owner | Due date | Status
D01 | Practice management system | Clients and contacts | People and organisations, with addresses, phone numbers, emails and identity records | 1850 | Migrate | Contacts | Merge duplicate contacts before the export. Keep former names as aliases. | Practice manager | 2026-11-05 | Not started
D02 | Practice management system | Open matters | Matter number, type, responsible lawyer, parties and status | 420 | Migrate | Matters | Matter numbers carry across unchanged. | Practice manager | 2026-11-04 | Not started
D03 | Practice management system | Closed matters | Matters closed within your retention period | 3100 | Archive | Archived matters (read-only) | Confirm the retention period with your law society or state bar. | Principal | 2026-11-04 | Not started
D04 | Practice management system | Matter types | Types and sub-types used to open matters | 38 | Migrate | Matter templates | Mapped to practice-area templates on Day 3. Retire types nobody uses. | Team leads | 2026-11-04 | Not started
D05 | Practice management system | Users and permissions | Staff, roles and access groups | 24 | Migrate | Users and roles | Leavers are not migrated. Their history stays on the matters. | Practice manager | 2026-11-05 | Not started
D06 | Practice management system | Billing rates | Rates by person, by matter and by activity | 60 | Migrate | Rate cards | Matter-specific rates override personal rates. | Bookkeeper | 2026-11-05 | Not started
D07 | Practice management system | Custom fields | Extra fields on matters and contacts | 45 | Migrate | Custom fields | Drop fields with no data in the last two years. | Practice manager | 2026-11-05 | Not started
D08 | Practice management system | Key dates | Limitation, hearing and settlement dates | 610 | Migrate | Key dates and reminders | Check every limitation date in the Day 8 sample. | Team leads | 2026-11-05 | Not started
D09 | Practice management system | Unbilled time | Time and fee entries not yet billed | 2300 | Migrate | Unbilled time | Agreed matter by matter on Day 7. | Bookkeeper | 2026-11-10 | Not started
D10 | Practice management system | Debtors | Unpaid and part-paid invoices | 140 | Migrate | Opening debtor balances | Agreed matter by matter on Day 7. | Bookkeeper | 2026-11-10 | Not started
D11 | Trust accounting system | Client trust ledgers | Balance and transaction history for each client ledger | 310 | Migrate | Trust ledgers | Opening balances checked on the Trust balance check tab. | Bookkeeper | 2026-11-09 | Not started
D12 | Document management system | Matter documents | Correspondence, drafts and signed documents | 85000 | Migrate | Matter documents | Folder structure mapped to matter folders. | Practice manager | 2026-11-06 | Not started
D13 | Document management system | Precedents | Letters and forms used across the firm | 120 | Migrate | Document templates | Replace old merge fields with the new ones. | Team leads | 2026-11-12 | Not started
D14 | Shared drive | Client folders outside the system | Documents saved outside the matter file | 6500 | Migrate | Matter documents | Match folders to matter numbers. List any that do not match. | Practice manager | 2026-11-03 | Not started
D15 | Spreadsheet | Limitation diary | Key dates kept outside the system | 75 | Migrate | Key dates and reminders | Compare with the key dates row above and remove duplicates. | Team leads | 2026-11-05 | Not started
D16 | Email | Shared mailboxes | Filed client emails |  | Leave | Stays in the email system | Count the folders and confirm who keeps access after go-live. | Practice manager | 2026-11-03 | Not started
D17 | Accounting software | General ledger | Office account, payroll and tax records |  | Leave | Stays in the accounting software | Connect the accounting integration after go-live. | Bookkeeper | 2026-11-03 | Not started
D18
D19
D20
D21
D22
D23
D24
D25
D26
D27

## Trust balance check
FILEBIRD TEMPLATES
Data migration planner
Tab 3: Trust balance check. Add a row for every client ledger with a balance, not only the large ones. Run it on Day 6 (staging) and again on Day 10 (final import). Enter the reconciled trust bank balance at the cut-off date in the shaded cell.
Filebird template. A starting point only: check it against your jurisdiction’s rules and your law society or state bar’s requirements.
Cut-off date (input) | Trust bank balance (input) | Total of ledgers, current system | Total of ledgers, Filebird | Difference | All agree? | Ledgers agreed
2026-11-02 | 90690.5 | 90690.5 | 90628.5 | -62 | No | 5 of 6
Client ledger | Matter number | Balance in current system at cut-off | Balance in Filebird after import | Difference | Agrees? | Owner (checked by) | Due date | Status | Notes
Example client A | M-1042 | 12500 | 12500 | 0 | Yes | Bookkeeper | 2026-11-09 | Done
Example client B | M-1057 | 3250 | 3250 | 0 | Yes | Bookkeeper | 2026-11-09 | Done
Example client C | M-1063 | 48000 | 48000 | 0 | Yes | Bookkeeper | 2026-11-09 | Done
Example client D | M-1071 | 1180 | 1118 | -62 | No | Bookkeeper | 2026-11-09 | In progress | Example of a difference: digits transposed in the import file. Correct it, re-import and recheck.
Example client E | M-1088 | 760.5 | 760.5 | 0 | Yes | Bookkeeper | 2026-11-09 | Done
Example client F | M-1090 | 25000 | 25000 | 0 | Yes | Bookkeeper | 2026-11-09 | Not started
Formulas:
Due date = IF([Cut-off date (input)]="","",WORKDAY(GoLive,-5))

## Sign-off log
FILEBIRD TEMPLATES
Data migration planner
Tab 4: Sign-off log. Nothing leaves your old system until the firm signs off. Record who approved each stage and when.
Filebird template. A starting point only: check it against your jurisdiction’s rules and your law society or state bar’s requirements.
Stages signed off |  | Next stage to sign off | Go-live date
0 of 10 |  | Data inventory confirmed | 2026-11-16
Stage | Stage name | What the firm is approving | Evidence checked | Owner (prepares it) | Due date | Status | Approved by (name and role) | Date approved | Notes
1 | Data inventory confirmed | Every source of data is listed, with a decision to migrate, archive or leave it. | Data inventory tab. Day 1 export row counts. | Practice manager | 2026-11-03 | Not started
2 | Mapping approved | Matter types, users, rates and custom fields land in the right place. | Mapping notes on the Data inventory tab. | Practice manager | 2026-11-05 | Not started
3 | Staging import checked | The test import is complete and every error is explained. | Import log. Row counts against the Day 1 export. | Filebird migration specialist | 2026-11-06 | Not started
4 | Trust balances agreed | Every client ledger agrees, and the total matches the reconciled trust bank balance. | Trust balance check tab. Last trust reconciliation. | Bookkeeper | 2026-11-09 | Not started
5 | Unbilled time and debtors agreed | Unbilled time and unpaid invoices match the current system, matter by matter. | Unbilled time and aged debtors reports from both systems. | Bookkeeper | 2026-11-10 | Not started
6 | Sample review passed | 20 matters checked in full. No open issue blocks go-live. | Sample list and issue log. | Team leads | 2026-11-11 | Not started
7 | Firm review complete | The fix list is cleared, or the firm accepts what remains. | Fix list. | Practice manager | 2026-11-12 | Not started
8 | Final import and recheck | The final import matches the final export, and trust balances agree again. | Trust balance check (final run). Row counts. | Filebird migration specialist | 2026-11-13 | Not started
9 | Go-live approved | The firm moves to Filebird on Monday and the current system becomes read-only. | Stages 1 to 8 signed off. | Practice manager | 2026-11-13 | Not started
10 | Old records kept | Read-only access or a full archive is kept for as long as your rules require. | Archive location and access list. | Practice manager | 2026-11-20 | Not started